## Notes
All items include GST unless otherwise stated.
Staging & Tranches
Land development assumed to be delivered in broad stages. Total land development costs allocated between stages, with each stage timed separately. This allows costs to be front loaded - reflecting typical delivery.
Vertical construction and unit sales assumed to be in tranches. Typical project may have 4 or 5 stages, however units are delivered in substages (i.e. tranches), only committing to say 5 or 6 units at any one time to limit capital and exposure. Modelling as smaller tranches is more aggressive (relative to overall stages) but provides a more accurate estimate of capital requirements and better reflects actual project delivery.
Tranches delivered in sequential order with a duration for each tranche and a lage between commencement of each tranche.
Because land development and vertical construction are delinked it is important to cross check timings to ensure reasonable i.e. not building units on undeveloped land. Front loading land development costs helps to mitigate this risk.
Capital
Model assumes all capital flows freely. This allows for better comparability between projects, however in practice capital flows may be restricted.
Retirement villages are regulated and to protect residents a Statutory Supervisor ('SS') is appointed to monitor the village including financial position, solvency etc. In short the SS will always need comfort that sufficient capital available and invested to complete the development. Will depend on project specific risk e.g. freehold vs operating lease, progress (100 units remaining or 10 units remaining) and funding structure. This may slightly delay the release of capital towards the backend of the project, however it is not expected to be prohibitive or material to returns hence it is ignored.
Debt & Leverage
Model is unleveraged. This is also for comparability and simplicity reasons. Funding structure and equity requirements can easily be inferred from peak capital and cashflow projections - refer output. If required, debt assumptions could be built into the model.
Note, becuase equity receives a preferred return (8% interest charge), introducing debt would not increase overall costs. Instead changes the cost structure, noting that the preferred return only applies to A-Class shareholders (so not a true cost for A-Class). Any reduction in preferred return for A-Class would be outweighed by improvement in overall outcomes from reduced equity requirements.
Growth & Inflation
Inflation inputs included for capital growth and CPI. Capital growth applies to ORA sales during development and ongiong unit turnover income. CPI applies to development costs during development (excl land) and the ground lease during operating phase.
To ensure consistency all items must be inflated. Not fair to apply inflation to ground lease but not the value of units / DMF. This doesn't prevent application of different inflation rates if for example believed that capital growth will lag CPI.
For transparency the impact of these assumptions are presented separately within the ORA Surplus calculations - refer Outputs.
Preferred Interest
Inputs to set how much is paid out vs accrued. To avoid dilution of Hāpai overall cash return typically target 4.5% paid and 3.5%.
Any amount accrued will be released at development completion as occurs in practice. However, whether paid out or accrued difference is immaterial.
Fees
Koau fees not included
Hāpai share of KPV fees (via 50% stake in KPVLP) not captured within the model. Conservative and acknowledges that there are costs associated with these fees and not all profit.
No allowance for KPV transaction fee threshold / rebate structure.
KPV operational management post development ($50k CPI adjusted) assumed to be covered by resident fees (fixed / floating).
KPV fees per JV Agreement attached below.
Operating Lease
Set as a % of assumed land value
Structure - flat (i.e. no rent reviews) during development, CPI catch up mechanism once development complete and annual CPI thereafter
Terminal Value & Discount Rate
Terminal value applies the same discount rate to both the unit turnover income and operating lease (if applicable).
The operating lease increases risk, which should be reflected in a higher discount rate relative to freehold.
Appropriate discount rate is highly subjective. The 'as if complete' valuation for Papamoa adopted a discount rate of 20%, reflecting the leasehold structure, lack of capital gains, lack of embedded value as a newly completed village and likely cashflow shortfalls in early years as units sold down. The latter two factors do not apply to a mature village (assumption of terminal value). Therefore, in lieu of additional information, would consider 17.5% appropriate for leasehold and 15% for freehold. Ultimately limited impact on IRR calculation.
Note in theory if valued the two components separately, applying different discount rates to different risk profiles (lease vs RV income), should produce the same answer. However, this is overly prescriptive and ignores that the lease is an inherent component of the village.

## Cover
Formatting Conventions
| Input | 1000 | Fundamental model inputs / assumptions, hardcoded value
| Technical Input | 1000 | Input values that determine model integrity / structure and should not be changed
| Calculation | 1000 | Stand-alone calculation or reference within sheet
| Linked | 1000 | Reference to a different sheet
| Sensitivity | 1000 | Input cell linked to sensivity analysis
| Blank |  | Cell left intentionally blank for a functional purpose, may have dependents
| Explanatory | ABC | Contextual support
| Note | ABC | Additional information

## Project Inputs
LAND
Details
|  | Model | Operating Lease | "Ownership" covers both freehold and pre-paid ground lease
|  | Land Area | 49109 | sqm
| Value |  | Per sqm | Total
|  | Value (excl GST) | 200 | 9821800
|  | Value (incl GST) | 230 | 11295070
Lease
|  | Cap Rate | 6% | applied to the GST inclusive land value
|  | Rental - annual (incl GST) | 677704.2
|  | Rental - period (incl GST) | 56475.35
DEVELOPMENT OVERVIEW
|  | Unit Type | Description | Typology | Bedrooms | Bathrooms | Garages | Floor Area | Value Ratio | Market Value | Quantity | Value Ratio Reworked | Value per SQm
|  | KDG | Standalone | House | 3 | 2 | 2 | 180 | 125% | 1313920.4545 | 0 | 142%
|  | HDG | Standalone | House | 3 | 2 | 2 | 180 | 102% | 1173579.5455 | 0 | 115.9%
|  | NDG | Standalone | House | 3 | 2 | 2 | 180 | 100% | 1150568.1818 | 0 | 113.6%
|  | BSG | 2 bed duplex | House | 2 | 1.5 | 1 | 121.6 | 78% | 925000 | 55 | 100% | 7606.9079
|  | JMSG | 2 bed duplex | House | 2 | 1.5 | 1 | 120.9 | 77% | 913141.0256 | 0 | 98.72%
|  | JMDG | 2 bed duplex | House | 2 | 1.5 | 2 | 137.1 | 80% | 948717.9487 | 0 | 102.6%
|  | ESG | 3 bed duplex | House | 3 | 2 | 1 | 133.4 | 88.5% | 1018252.8409 | 0 | 100.6%
|  | MSG | 3 bed duplex | House | 3 | 2 | 1 | 139.33 | 88.7% | 1020553.9773 | 0 | 100.8%
|  | MNSG | 3 bed duplex | House | 3 | 2 | 1 | 144.2 | 88% | 1012500 | 36 | 100% | 7021.4979
|  | LSG | 3 bed duplex | House | 3 | 2 | 1 | 145.67 | 88% | 1012500 | 0 | 100%
|  | MDG | 3 bed duplex | House | 3 | 2 | 2 | 155.58 | 96% | 1104545.4545 | 0 | 109.1%
|  | R6 | Six unit duplex | House | 2 | 1.5 | 1 | 108.33 | 70% | 830128.2051 | 0 | 89.74%
|  | S1 | Stanaway | Apartment | 2 | 2 | 1 | 148.6961 | 86% | 1019871.7949 | 0 | 110.3%
|  | S2 | Stanaway | Apartment | 2 | 2 | 1 | 139.606 | 86% | 1019871.7949 | 0 | 110.3%
|  | S3 | Stanaway | Apartment | 2 | 2 | 1 | 152.2177 | 92% | 1091025.641 | 0 | 117.9%
|  | S4 | Stanaway | Apartment | 3.5 | 2 | 1 | 238.7833 | 89% | 0 | 0 | N/A
|  | S5 | Stanaway | Apartment | 2.5 | 2 | 1 | 198.647 | 92% | 0 | 0 | N/A
|  | Total / Weighted Average | [7 empty] | 959615.3846 | 91
|  | Base Value 2 Bedroom Units | 925000
|  | Base Value 3 Bedroom Units | 1012500
VERTICAL CONSTRUCTION
|  | Input Build Rate (psm) (incl GST) | 3718.6475
|  | Sensitivity | 0%
|  | Applied Build Rate (psm) (incl GST) | 3718.6475
|  | Apartment Premium | 40%
Costs
|  |  | House | Apartment | Total
|  | Build Rate (psm) (incl GST) | 3718.6475 | 5206.1066 | 3718.6475
|  | Floor Area | 11879.2 | 0 | 11879.2
|  | Total Cost (incl GST) | 44174557.8689 | 0 | 44174557.8689
LAND DEVELOPMENT
Costs
|  |  | Base |  | Rate (excl GST) | Total (excl GST) | Total (incl GST)
|  | P&G per stage | 3 |  | 55000 | 165000 | 189750
|  | Landscaping | 91 | units | 20000 | 1820000 | 2093000
|  | Signage and Entrance | 1 |  | 40000 | 40000 | 46000
|  | Fencing frontage | 275 |  | 400 | 110000 | 126500
|  | Fencing back | 175 |  | 400 | 70000 | 80500
|  | Roading Internal | 91 | units | 11000 | 1001000 | 1151150
|  | Sewer | 91 | units | 4500 | 409500 | 470925
|  | Stormwater | 91 | units | 6100 | 555100 | 638365
|  | Water Mains reticulation | 91 | units | 3500 | 318500 | 366275
|  | Earthworks & land remediation | 91 | units | 45000 | 4095000 | 4709250
|  | Additional earthworks to foreshore | 10000 |  | 20 | 200000 | 230000
|  | Clearance & sediment control | 49109 | sqm | 4 | 196436 | 225901.4
|  | Sloping land retaining walls | 12000 |  | 30 | 360000 | 414000
|  | Power | 91 | units | 8000 | 728000 | 837200
|  | Streetlights | 45.5 | units / 2 | 3500 | 159250 | 183137.5
|  | Fibre | 91 | units | 500 | 45500 | 52325
|  | Nursecall/Security System | 91 | units | 4500 | 409500 | 470925
|  | Total |  |  |  | 10682786 | 12285203.9
135002.2407
COMMUNITY CENTRE
Residents
|  | Units | 91
|  | Average residents per unit | 1.7
|  | Total residents (estimate) | 154.7
Community Centre Components
Area Required
|  | Hospital | 0 | n/a
|  | Dining room | 309.4 | 2sqm per resident
|  | Kitchen | 36.4 | 20sqm per x50 units
|  | Toilets | 61.88 | 4sqm per x10 residentsunits
|  | Games | 63.7 | 35sqm per x50 units
|  | Changing & Shower | 36.4 | 20sqm per x50 units
|  | Gym | 10.92 | 30% of gym
|  | Pool area | 200 | hardcode
|  | Admin and Staff area | 50 | hardcode
|  | Total | 768.7
Village Rating
|  | Village Star Rating | 4.5
|  | Rating | Garden area | Garden Costs | Pavilion cost | Fit out cost
|  | 4.5 | 24 | 250 | 7000 | 800
|  | 4 | 22 | 235 | 6000 | 667
|  | 3.5 | 20 | 217 | 5000 | 533
|  | 3 | 18 | 200 | 4000 | 400
Costs
|  |  | Base |  | Rate (incl GST) | Total (incl GST)
|  | Pavilion Cost | 768.7 | sqm | 5000 | 3843500
|  | Pavilion Design | 3843500 |  | 0.1 | 384350
|  | Fit out cost | 768.7 | sqm | 1500 | 1153050
|  | Visitor parking | 15.47 | 1 per 10 residents | 3705 | 57316.35
|  | Communal Gardens | 2184 |  | 250 | 546000
|  | Breathing spaces | 0 |  | 0 | 0
|  | Bowling green | 5 | lanes | 60000 | 300000
|  | Swimming Pool | 0 |  | 0 | 0
|  | Workshop | 75 |  | 400 | 30000
|  | Contingency | 6314216.35 |  | 10% | 631421.635
|  | Total |  |  |  | 6945637.985
PRELIMINARY COSTS
|  |  | Base |  | Rate (incl GST) | Total (incl GST)
Finance
|  | Bank fee | 1 |  | 80000 | 80000
|  | Legal | 1 |  | 50000 | 50000
|  | Valuation | 1 |  | 25000 | 25000
Registration
|  | Legal | 1 |  | 30000 | 30000
|  | Trustee | 1 |  | 20000 | 20000
Council Fees
|  | Resource consent | 1 |  | 500000 | 500000
|  | Development & Financial Contribution | 91 |  | 25000 | 2275000
Other
|  | Detailed design - initial | 20 | units | 7000 | 140000
|  | Preliminary | 1 |  | 20000 | 20000
|  | Supervision | 91 |  | 4500 | 409500
|  | Hearing costs | 1 |  | 60000 | 60000
|  | Total Preliminary Costs |  |  |  | 3609500
HOLDING & OTHER COSTS
|  |  | Base |  | Rate (incl GST) | Total (incl GST)
|  | Detailed design - subsequent | 91 | units | 5700 | 518700
|  | Annual operating deficit | 637 | $500/unit pa | 500 | 318500
|  | Rates / insurance | 637 | $35/unit pa | 35 | 22295
|  | Marketing | 1 |  | 1500000 | 1500000 |  | To check: does this include commissions?
|  | Total Holding & Other Costs |  |  |  | 2359495
FEES
Refer Model Inputs - Operating for resale fee
|  | KPV Transcation Fee | 1% | 1.0% of budgeted development cost (including land value)
|  | KPV Processing Fee | 1.5% | 1.5% + GST (NB: 1.5% applied to GST incl costs so the "plus GST") is automatically captured
|  | KPV Project Management (development) | 150000 | p.a.
|  | KPV Operational Management (development) | 150000 | p.a.
STAGING & TIMING
Land Development
|  |  | Commencement | Duration | Allocation
|  | Stage 1 | 6 | 8 | 40%
|  | Stage 2 | 18 | 6 | 30%
|  | Stage 3 | 30 | 6 | 30%
|  | Stage 4 | 0 | 0 | 0%
|  | Stage 5 | 0 | 0 | 0%
Vertical Construction
Timing
|  | Commencement | 16 | month
|  | Construction Duration | 3 | months per tranche
|  | Lag | 3 | months between commencement of tranches
|  | Sales lag | 3 | months post completion
Tranches
|  | Tranche Size | 6
|  | Tranches | 16
|  | Tranches | Units |  |  | Total duration
|  | 1 | 6
|  | 2 | 6
|  | 3 | 6
|  | 4 | 6
|  | 5 | 6
|  | 6 | 6
|  | 7 | 6
|  | 8 | 6
|  | 9 | 6
|  | 10 | 6
|  | 11 | 6
|  | 12 | 6
|  | 13 | 6
|  | 14 | 6
|  | 15 | 6
|  | 16 | 1
|  | 17 | 0
|  | 18 | 0
|  | 19 | 0
|  | 20 | 0
|  | 21 | 0
|  | 22 | 0
|  | 23 | 0
|  | 24 | 0
|  | 25 | 0
Other
|  |  | Commencement | Duration
|  | Land Acquisition | 1 | 1
|  | Preliminary Costs | 2 | 4
|  | Community Centre | 24 | 9
|  | KPV Transaction Fee | 1 | 1
Note on E45: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Whats in this???
Note on D156: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Does this include - commission, if not, this is rich.
Note on H191: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: For your staging - 1 house = 16 weeks start to finish, then you should get an additional house every 2 weeks following (aggressive).

## Model Inputs
GENERAL
|  | Model Commencement Date | 2026-06-30 | placeholder for XIRR
|  | Model Term | 15 | years
|  | Periodicity | 12 | 1 = annually; 2 = biannually; 4 = quarterly; 12 = monthly
STRUCTURE
Share Class Structure
|  | A Class | 70%
|  | B Class | 30%
A Class Share Allocation
|  | Hāpai | 100%
|  | Vendor | 0%
B Class Share Allocation
|  | Hāpai | 50%
|  | KPV | 50%
Shareholdings
|  |  | Hāpai | KPV | Vendor | Total
|  | A-Class | 70% | 0% | 0% | 70%
|  | B-Class | 15% | 15% | 0% | 30%
|  | Total | 85% | 15% | 0% | 100%
Preferred Interest (A-Class)
|  | Paid | 4.5%
|  | Accrued | 3.5%
|  | Total | 8%
OPERATING
Unit Turnover
|  | Average Resident Tenure | 8 | years
|  | Average DMF | 15%
|  | Resale Fee | 1%
Turnover Scaling
|  | 1 | 20%
|  | 2 | 40%
|  | 3 | 60%
|  | 4 | 80%
|  | 5 | 100%
|  | 6 | 100%
|  | 7 | 100%
|  | 8 | 100%
|  | 9 | 100%
|  | 10 | 100%
|  | 11 | 100%
|  | 12 | 100%
|  | 13 | 100%
|  | 14 | 100%
|  | 15 | 100%
Terminal Value
|  | Discount Rate | 17.5%
GROWTH & INFLATION
|  | Capital Growth | 2%
|  | Inflation - Costs | 2%
|  | Inflation - Lease | 2%
DATA VALIDATION REFERENCES
|  | Land | Ownership | Operating Lease
|  | Typology | House | Apartment
|  | Village Star Rating | 3 | 3.5 | 4 | 4.5

## Cashflow
|  | Period |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143 | 144 | 145 | 146 | 147 | 148 | 149 | 150 | 151 | 152 | 153 | 154 | 155 | 156 | 157 | 158 | 159 | 160 | 161 | 162 | 163 | 164 | 165 | 166 | 167 | 168 | 169 | 170 | 171 | 172 | 173 | 174 | 175 | 176 | 177 | 178 | 179 | 180
Date | time axis 2026-06-30 to 2041-05-31
|  | Development Phase |  |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Operating Phase |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  | Project Year |  |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
|  | Operating Year |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
|  | Inflation Factor - Capital Growth |  |  |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 102% | 102% | 102% | 102% | 102% | 102% | 102% | 102% | 102% | 102% | 102% | 102% | 104% | 104% | 104% | 104% | 104% | 104% | 104% | 104% | 104% | 104% | 104% | 104% | 106.1% | 106.1% | 106.1% | 106.1% | 106.1% | 106.1% | 106.1% | 106.1% | 106.1% | 106.1% | 106.1% | 106.1% | 108.2% | 108.2% | 108.2% | 108.2% | 108.2% | 108.2% | 108.2% | 108.2% | 108.2% | 108.2% | 108.2% | 108.2% | 110.4% | 110.4% | 110.4% | 110.4% | 110.4% | 110.4% | 110.4% | 110.4% | 110.4% | 110.4% | 110.4% | 110.4% | 112.6% | 112.6% | 112.6% | 112.6% | 112.6% | 112.6% | 112.6% | 112.6% | 112.6% | 112.6% | 112.6% | 112.6% | 114.9% | 114.9% | 114.9% | 114.9% | 114.9% | 114.9% | 114.9% | 114.9% | 114.9% | 114.9% | 114.9% | 114.9% | 117.2% | 117.2% | 117.2% | 117.2% | 117.2% | 117.2% | 117.2% | 117.2% | 117.2% | 117.2% | 117.2% | 117.2% | 119.5% | 119.5% | 119.5% | 119.5% | 119.5% | 119.5% | 119.5% | 119.5% | 119.5% | 119.5% | 119.5% | 119.5% | 121.9% | 121.9% | 121.9% | 121.9% | 121.9% | 121.9% | 121.9% | 121.9% | 121.9% | 121.9% | 121.9% | 121.9% | 124.3% | 124.3% | 124.3% | 124.3% | 124.3% | 124.3% | 124.3% | 124.3% | 124.3% | 124.3% | 124.3% | 124.3% | 126.8% | 126.8% | 126.8% | 126.8% | 126.8% | 126.8% | 126.8% | 126.8% | 126.8% | 126.8% | 126.8% | 126.8% | 129.4% | 129.4% | 129.4% | 129.4% | 129.4% | 129.4% | 129.4% | 129.4% | 129.4% | 129.4% | 129.4% | 129.4% | 131.9% | 131.9% | 131.9% | 131.9% | 131.9% | 131.9% | 131.9% | 131.9% | 131.9% | 131.9% | 131.9% | 131.9%
|  | Inflation Factor - Costs |  |  |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 102% | 102% | 102% | 102% | 102% | 102% | 102% | 102% | 102% | 102% | 102% | 102% | 104% | 104% | 104% | 104% | 104% | 104% | 104% | 104% | 104% | 104% | 104% | 104% | 106.1% | 106.1% | 106.1% | 106.1% | 106.1% | 106.1% | 106.1% | 106.1% | 106.1% | 106.1% | 106.1% | 106.1% | 108.2% | 108.2% | 108.2% | 108.2% | 108.2% | 108.2% | 108.2% | 108.2% | 108.2% | 108.2% | 108.2% | 108.2% | 110.4% | 110.4% | 110.4% | 110.4% | 110.4% | 110.4% | 110.4% | 110.4% | 110.4% | 110.4% | 110.4% | 110.4% | 112.6% | 112.6% | 112.6% | 112.6% | 112.6% | 112.6% | 112.6% | 112.6% | 112.6% | 112.6% | 112.6% | 112.6% | 114.9% | 114.9% | 114.9% | 114.9% | 114.9% | 114.9% | 114.9% | 114.9% | 114.9% | 114.9% | 114.9% | 114.9% | 117.2% | 117.2% | 117.2% | 117.2% | 117.2% | 117.2% | 117.2% | 117.2% | 117.2% | 117.2% | 117.2% | 117.2% | 119.5% | 119.5% | 119.5% | 119.5% | 119.5% | 119.5% | 119.5% | 119.5% | 119.5% | 119.5% | 119.5% | 119.5% | 121.9% | 121.9% | 121.9% | 121.9% | 121.9% | 121.9% | 121.9% | 121.9% | 121.9% | 121.9% | 121.9% | 121.9% | 124.3% | 124.3% | 124.3% | 124.3% | 124.3% | 124.3% | 124.3% | 124.3% | 124.3% | 124.3% | 124.3% | 124.3% | 126.8% | 126.8% | 126.8% | 126.8% | 126.8% | 126.8% | 126.8% | 126.8% | 126.8% | 126.8% | 126.8% | 126.8% | 129.4% | 129.4% | 129.4% | 129.4% | 129.4% | 129.4% | 129.4% | 129.4% | 129.4% | 129.4% | 129.4% | 129.4% | 131.9% | 131.9% | 131.9% | 131.9% | 131.9% | 131.9% | 131.9% | 131.9% | 131.9% | 131.9% | 131.9% | 131.9%
|  | Inflation Factor - Lease |  |  |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 102% | 102% | 102% | 102% | 102% | 102% | 102% | 102% | 102% | 102% | 102% | 102% | 104% | 104% | 104% | 104% | 104% | 104% | 104% | 104% | 104% | 104% | 104% | 104% | 106.1% | 106.1% | 106.1% | 106.1% | 106.1% | 106.1% | 106.1% | 106.1% | 106.1% | 106.1% | 106.1% | 106.1% | 108.2% | 108.2% | 108.2% | 108.2% | 108.2% | 108.2% | 108.2% | 108.2% | 108.2% | 108.2% | 108.2% | 108.2% | 110.4% | 110.4% | 110.4% | 110.4% | 110.4% | 110.4% | 110.4% | 110.4% | 110.4% | 110.4% | 110.4% | 110.4% | 112.6% | 112.6% | 112.6% | 112.6% | 112.6% | 112.6% | 112.6% | 112.6% | 112.6% | 112.6% | 112.6% | 112.6% | 114.9% | 114.9% | 114.9% | 114.9% | 114.9% | 114.9% | 114.9% | 114.9% | 114.9% | 114.9% | 114.9% | 114.9% | 117.2% | 117.2% | 117.2% | 117.2% | 117.2% | 117.2% | 117.2% | 117.2% | 117.2% | 117.2% | 117.2% | 117.2% | 119.5% | 119.5% | 119.5% | 119.5% | 119.5% | 119.5% | 119.5% | 119.5% | 119.5% | 119.5% | 119.5% | 119.5% | 121.9% | 121.9% | 121.9% | 121.9% | 121.9% | 121.9% | 121.9% | 121.9% | 121.9% | 121.9% | 121.9% | 121.9% | 124.3% | 124.3% | 124.3% | 124.3% | 124.3% | 124.3% | 124.3% | 124.3% | 124.3% | 124.3% | 124.3% | 124.3% | 126.8% | 126.8% | 126.8% | 126.8% | 126.8% | 126.8% | 126.8% | 126.8% | 126.8% | 126.8% | 126.8% | 126.8% | 129.4% | 129.4% | 129.4% | 129.4% | 129.4% | 129.4% | 129.4% | 129.4% | 129.4% | 129.4% | 129.4% | 129.4% | 131.9% | 131.9% | 131.9% | 131.9% | 131.9% | 131.9% | 131.9% | 131.9% | 131.9% | 131.9% | 131.9% | 131.9%
TIMING
| Land Development - Stages & Allocation |  | Allocation |  | Commencement | Duration
|  | Stage 1 | 40% |  | 6 | 8 | bar: 2026-06-30 to 2041-05-31
|  | Stage 2 | 30% |  | 18 | 6 | bar: 2026-06-30 to 2041-05-31
|  | Stage 3 | 30% |  | 30 | 6 | bar: 2026-06-30 to 2041-05-31
|  | Stage 4 | 0% |  | 0 | 0 | bar: 2026-06-30 to 2041-05-31
|  | Stage 5 | 0% |  | 0 | 0 | bar: 2026-06-30 to 2041-05-31
[7 empty] | 0% | 0% | 0% | 0% | 0% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 0% | 0% | 0% | 0% | 5% | 5% | 5% | 5% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 5% | 5% | 5% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Vertical Construction - Timing |  |  |  | Commencement | Duration
|  | 1 |  |  | 16 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2 |  |  | 19 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3 |  |  | 22 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4 |  |  | 25 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 5 |  |  | 28 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 6 |  |  | 31 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 7 |  |  | 34 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 8 |  |  | 37 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 9 |  |  | 40 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 10 |  |  | 43 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 11 |  |  | 46 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 12 |  |  | 49 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 13 |  |  | 52 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 14 |  |  | 55 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 15 |  |  | 58 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 16 |  |  | 61 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Vertical Construction - Completion |  | Units |  | Completion
|  | 1 | 6 |  | 18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2 | 6 |  | 21 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3 | 6 |  | 24 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4 | 6 |  | 27 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 5 | 6 |  | 30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 6 | 6 |  | 33 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 7 | 6 |  | 36 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 8 | 6 |  | 39 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 9 | 6 |  | 42 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 10 | 6 |  | 45 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 11 | 6 |  | 48 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 12 | 6 |  | 51 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 13 | 6 |  | 54 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 14 | 6 |  | 57 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 15 | 6 |  | 60 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 16 | 1 |  | 63 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 6 | 0 | 0 | 6 | 0 | 0 | 6 | 0 | 0 | 6 | 0 | 0 | 6 | 0 | 0 | 6 | 0 | 0 | 6 | 0 | 0 | 6 | 0 | 0 | 6 | 0 | 0 | 6 | 0 | 0 | 6 | 0 | 0 | 6 | 0 | 0 | 6 | 0 | 0 | 6 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sales |  | Units |  | Sale
|  | 1 | 6 |  | 21 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2 | 6 |  | 24 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3 | 6 |  | 27 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4 | 6 |  | 30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 5 | 6 |  | 33 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 6 | 6 |  | 36 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 7 | 6 |  | 39 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 8 | 6 |  | 42 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 9 | 6 |  | 45 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 10 | 6 |  | 48 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 11 | 6 |  | 51 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 12 | 6 |  | 54 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 13 | 6 |  | 57 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 14 | 6 |  | 60 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 15 | 6 |  | 63 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 16 | 1 |  | 66 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 6 | 0 | 0 | 6 | 0 | 0 | 6 | 0 | 0 | 6 | 0 | 0 | 6 | 0 | 0 | 6 | 0 | 0 | 6 | 0 | 0 | 6 | 0 | 0 | 6 | 0 | 0 | 6 | 0 | 0 | 6 | 0 | 0 | 6 | 0 | 0 | 6 | 0 | 0 | 6 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DEVELOPMENT
| Development Cashflows |  | Costs / Ref |  | Commencement | Duration
|  | Land | 0 |  | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Ground Lease | -56475.35 |  | Spread through development phase |  | -56475.35 | -56475.35 | -56475.35 | -56475.35 | -56475.35 | -56475.35 | -56475.35 | -56475.35 | -56475.35 | -56475.35 | -56475.35 | -56475.35 | -56475.35 | -56475.35 | -56475.35 | -56475.35 | -56475.35 | -56475.35 | -56475.35 | -56475.35 | -56475.35 | -56475.35 | -56475.35 | -56475.35 | -56475.35 | -56475.35 | -56475.35 | -56475.35 | -56475.35 | -56475.35 | -56475.35 | -56475.35 | -56475.35 | -56475.35 | -56475.35 | -56475.35 | -56475.35 | -56475.35 | -56475.35 | -56475.35 | -56475.35 | -56475.35 | -56475.35 | -56475.35 | -56475.35 | -56475.35 | -56475.35 | -56475.35 | -56475.35 | -56475.35 | -56475.35 | -56475.35 | -56475.35 | -56475.35 | -56475.35 | -56475.35 | -56475.35 | -56475.35 | -56475.35 | -56475.35 | -56475.35 | -56475.35 | -56475.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Preliminary Costs | -3609500 |  | 2 | 4 | 0 | -902375 | -902375 | -902375 | -902375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land Development | -12285203.9 |  | Refer timing above |  | 0 | 0 | 0 | 0 | 0 | -614260.195 | -614260.195 | -614260.195 | -614260.195 | -614260.195 | -614260.195 | -614260.195 | -614260.195 | 0 | 0 | 0 | 0 | -614260.195 | -614260.195 | -614260.195 | -614260.195 | -614260.195 | -614260.195 | 0 | 0 | 0 | 0 | 0 | 0 | -614260.195 | -614260.195 | -614260.195 | -614260.195 | -614260.195 | -614260.195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Vertical Construction | -44174557.8689 |  | Refer timing above |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -920303.2889 | -920303.2889 | -920303.2889 | -920303.2889 | -920303.2889 | -920303.2889 | -920303.2889 | -920303.2889 | -920303.2889 | -920303.2889 | -920303.2889 | -920303.2889 | -920303.2889 | -920303.2889 | -920303.2889 | -920303.2889 | -920303.2889 | -920303.2889 | -920303.2889 | -920303.2889 | -920303.2889 | -920303.2889 | -920303.2889 | -920303.2889 | -920303.2889 | -920303.2889 | -920303.2889 | -920303.2889 | -920303.2889 | -920303.2889 | -920303.2889 | -920303.2889 | -920303.2889 | -920303.2889 | -920303.2889 | -920303.2889 | -920303.2889 | -920303.2889 | -920303.2889 | -920303.2889 | -920303.2889 | -920303.2889 | -920303.2889 | -920303.2889 | -920303.2889 | -920303.2889 | -920303.2889 | -920303.2889 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Community Centre | -6945637.985 |  | 24 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -771737.5539 | -771737.5539 | -771737.5539 | -771737.5539 | -771737.5539 | -771737.5539 | -771737.5539 | -771737.5539 | -771737.5539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Holding & Other | -2359495 |  | Spread through development phase |  | -37452.3016 | -37452.3016 | -37452.3016 | -37452.3016 | -37452.3016 | -37452.3016 | -37452.3016 | -37452.3016 | -37452.3016 | -37452.3016 | -37452.3016 | -37452.3016 | -37452.3016 | -37452.3016 | -37452.3016 | -37452.3016 | -37452.3016 | -37452.3016 | -37452.3016 | -37452.3016 | -37452.3016 | -37452.3016 | -37452.3016 | -37452.3016 | -37452.3016 | -37452.3016 | -37452.3016 | -37452.3016 | -37452.3016 | -37452.3016 | -37452.3016 | -37452.3016 | -37452.3016 | -37452.3016 | -37452.3016 | -37452.3016 | -37452.3016 | -37452.3016 | -37452.3016 | -37452.3016 | -37452.3016 | -37452.3016 | -37452.3016 | -37452.3016 | -37452.3016 | -37452.3016 | -37452.3016 | -37452.3016 | -37452.3016 | -37452.3016 | -37452.3016 | -37452.3016 | -37452.3016 | -37452.3016 | -37452.3016 | -37452.3016 | -37452.3016 | -37452.3016 | -37452.3016 | -37452.3016 | -37452.3016 | -37452.3016 | -37452.3016 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | KPV Processing Fee | 1.5% |  | Linked to other costs |  | -561.7845 | -14097.4095 | -14097.4095 | -14097.4095 | -14097.4095 | -9775.6874 | -9775.6874 | -9775.6874 | -9775.6874 | -9775.6874 | -9775.6874 | -9775.6874 | -9775.6874 | -561.7845 | -561.7845 | -14366.3339 | -14366.3339 | -23580.2368 | -23580.2368 | -23580.2368 | -23580.2368 | -23580.2368 | -23580.2368 | -25942.3972 | -25942.3972 | -25942.3972 | -25942.3972 | -25942.3972 | -25942.3972 | -35156.3001 | -35156.3001 | -35156.3001 | -23580.2368 | -23580.2368 | -23580.2368 | -14366.3339 | -14366.3339 | -14366.3339 | -14366.3339 | -14366.3339 | -14366.3339 | -14366.3339 | -14366.3339 | -14366.3339 | -14366.3339 | -14366.3339 | -14366.3339 | -14366.3339 | -14366.3339 | -14366.3339 | -14366.3339 | -14366.3339 | -14366.3339 | -14366.3339 | -14366.3339 | -14366.3339 | -14366.3339 | -14366.3339 | -14366.3339 | -14366.3339 | -14366.3339 | -14366.3339 | -14366.3339 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | KPV Transaction Fee | -806694.6475 |  | 1 | 1 | -806694.6475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | KPV Management Fee | -300000 | p.a. | Spread through development phase |  | -25000 | -25000 | -25000 | -25000 | -25000 | -25000 | -25000 | -25000 | -25000 | -25000 | -25000 | -25000 | -25000 | -25000 | -25000 | -25000 | -25000 | -25000 | -25000 | -25000 | -25000 | -25000 | -25000 | -25000 | -25000 | -25000 | -25000 | -25000 | -25000 | -25000 | -25000 | -25000 | -25000 | -25000 | -25000 | -25000 | -25000 | -25000 | -25000 | -25000 | -25000 | -25000 | -25000 | -25000 | -25000 | -25000 | -25000 | -25000 | -25000 | -25000 | -25000 | -25000 | -25000 | -25000 | -25000 | -25000 | -25000 | -25000 | -25000 | -25000 | -25000 | -25000 | -25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Inflation - Cost |  |  | Refer inflation factors |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -13729.7637 | -1260.2817 | -1260.2817 | -19942.4385 | -19942.4385 | -32411.9204 | -32411.9204 | -32411.9204 | -32411.9204 | -32411.9204 | -32411.9204 | -35608.7108 | -71929.5959 | -71929.5959 | -71929.5959 | -71929.5959 | -71929.5959 | -97117.9494 | -97117.9494 | -97117.9494 | -65472.0793 | -65472.0793 | -65472.0793 | -40283.7257 | -61031.8387 | -61031.8387 | -61031.8387 | -61031.8387 | -61031.8387 | -61031.8387 | -61031.8387 | -61031.8387 | -61031.8387 | -61031.8387 | -61031.8387 | -61031.8387 | -82194.914 | -82194.914 | -82194.914 | -82194.914 | -82194.914 | -82194.914 | -82194.914 | -82194.914 | -82194.914 | -82194.914 | -82194.914 | -82194.914 | -103781.2508 | -103781.2508 | -103781.2508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Preferred Interest |  |  | Refer calculations below |  | 0 | -3473.1903 | -7379.0951 | -11311.0393 | -15269.1965 | -19253.7414 | -22168.2129 | -25102.1142 | -28055.5749 | -31028.7253 | -34021.6968 | -37034.6213 | -40067.6321 | -43172.3495 | -43912.9766 | -44658.5412 | -48982.0387 | -53334.3596 | -60100.4843 | -66911.7166 | -73768.357 | -59079.3623 | -65883.787 | -72733.5746 | -58649.0675 | -66198.2131 | -73797.6863 | -59856.4766 | -67413.6716 | -75021.2479 | -63520.6794 | -73534.7866 | -83615.6546 | -69116.284 | -76111.5972 | -83153.5458 | -66218.6104 | -70839.9269 | -75492.0523 | -58583.8457 | -63154.2638 | -67755.1514 | -50795.3654 | -55313.8604 | -59862.4786 | -42850.0748 | -47315.6012 | -51810.8977 | -34744.8167 | -39235.6695 | -43756.4614 | -26716.0457 | -31153.3733 | -35620.2832 | -18525.6263 | -22908.3512 | -27320.2942 | -10170.3041 | -14497.3268 | -18853.1964 | -8138.0401 | -8161.776 | -2201374.1283 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | -926184.0836 | -1038873.2514 | -1042779.1563 | -1046711.1005 | -1050669.2576 | -762217.2754 | -765131.7469 | -768065.6483 | -771019.109 | -773992.2594 | -776985.2308 | -779998.1554 | -796760.9298 | -163922.0673 | -164662.6944 | -1118198.2541 | -1122521.7516 | -1762817.6523 | -1769583.7771 | -1776395.0093 | -1783251.6498 | -1768562.655 | -1775367.0798 | -1945253.177 | -1967489.5549 | -1975038.7005 | -1982638.1738 | -1968696.964 | -1976254.159 | -2632524.1868 | -2621023.6183 | -2631037.7256 | -1826159.1062 | -1811659.7356 | -1818655.0488 | -1177034.5459 | -1180847.7235 | -1185469.0401 | -1190121.1654 | -1173212.9588 | -1177783.3769 | -1182384.2645 | -1165424.4786 | -1169942.9735 | -1174491.5918 | -1157479.188 | -1161944.7143 | -1166440.0108 | -1170537.0051 | -1175027.8579 | -1179548.6498 | -1162508.234 | -1166945.5617 | -1171412.4716 | -1154317.8147 | -1158700.5396 | -1163112.4826 | -1145962.4925 | -1150289.5152 | -1154645.3848 | -1165516.5653 | -1165540.3012 | -3358752.6534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | ORA Sales | 959615.3846 |  | Refer timing above |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5757692.3077 | 0 | 0 | 5757692.3077 | 0 | 0 | 5757692.3077 | 0 | 0 | 5757692.3077 | 0 | 0 | 5757692.3077 | 0 | 0 | 5757692.3077 | 0 | 0 | 5757692.3077 | 0 | 0 | 5757692.3077 | 0 | 0 | 5757692.3077 | 0 | 0 | 5757692.3077 | 0 | 0 | 5757692.3077 | 0 | 0 | 5757692.3077 | 0 | 0 | 5757692.3077 | 0 | 0 | 5757692.3077 | 0 | 0 | 5757692.3077 | 0 | 0 | 959615.3846 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Inflation - ORA |  |  | Refer inflation factors |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115153.8462 | 0 | 0 | 115153.8462 | 0 | 0 | 232610.7692 | 0 | 0 | 232610.7692 | 0 | 0 | 232610.7692 | 0 | 0 | 232610.7692 | 0 | 0 | 352416.8308 | 0 | 0 | 352416.8308 | 0 | 0 | 352416.8308 | 0 | 0 | 352416.8308 | 0 | 0 | 474619.0135 | 0 | 0 | 474619.0135 | 0 | 0 | 474619.0135 | 0 | 0 | 474619.0135 | 0 | 0 | 599265.24 | 0 | 0 | 99877.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Net Development Cashflows |  |  |  |  | -926184.0836 | -1038873.2514 | -1042779.1563 | -1046711.1005 | -1050669.2576 | -762217.2754 | -765131.7469 | -768065.6483 | -771019.109 | -773992.2594 | -776985.2308 | -779998.1554 | -796760.9298 | -163922.0673 | -164662.6944 | -1118198.2541 | -1122521.7516 | -1762817.6523 | -1769583.7771 | -1776395.0093 | 3974440.6579 | -1768562.655 | -1775367.0798 | 3812439.1307 | -1967489.5549 | -1975038.7005 | 3775054.1339 | -1968696.964 | -1976254.159 | 3125168.1209 | -2621023.6183 | -2631037.7256 | 3931533.2015 | -1811659.7356 | -1818655.0488 | 4580657.7618 | -1180847.7235 | -1185469.0401 | 4567571.1423 | -1173212.9588 | -1177783.3769 | 4575308.0431 | -1165424.4786 | -1169942.9735 | 4583200.7159 | -1157479.188 | -1161944.7143 | 4591252.2969 | -1170537.0051 | -1175027.8579 | 4578143.6579 | -1162508.234 | -1166945.5617 | 4586279.8361 | -1154317.8147 | -1158700.5396 | 4594579.8251 | -1145962.4925 | -1150289.5152 | 4603046.9229 | -1165516.5653 | -1165540.3012 | 2398939.6543 | 0 | 0 | 959615.3846 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FUNDING
Funding Stack
|  | Cumulative Development Cashflows |  |  |  |  | -926184.0836 | -1965057.3351 | -3007836.4913 | -4054547.5918 | -5105216.8494 | -5867434.1248 | -6632565.8717 | -7400631.52 | -8171650.629 | -8945642.8883 | -9722628.1191 | -10502626.2745 | -11299387.2043 | -11463309.2716 | -11627971.966 | -12746170.22 | -13868691.9716 | -15631509.6239 | -17401093.401 | -19177488.4103 | -15203047.7524 | -16971610.4074 | -18746977.4872 | -14934538.3565 | -16902027.9114 | -18877066.612 | -15102012.4781 | -17070709.4421 | -19046963.6011 | -15921795.4803 | -18542819.0986 | -21173856.8242 | -17242323.6226 | -19053983.3583 | -20872638.4071 | -16291980.6453 | -17472828.3688 | -18658297.4089 | -14090726.2666 | -15263939.2254 | -16441722.6024 | -11866414.5592 | -13031839.0378 | -14201782.0113 | -9618581.2954 | -10776060.4834 | -11938005.1977 | -7346752.9008 | -8517289.9059 | -9692317.7638 | -5114174.1059 | -6276682.3399 | -7443627.9017 | -2857348.0656 | -4011665.8802 | -5170366.4198 | -575786.5947 | -1721749.0872 | -2872038.6024 | 1731008.3205 | 565491.7553 | -600048.5459 | 1798891.1083 | 1798891.1083 | 1798891.1083 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493
|  | Investor Capital |  |  |  |  | 926184.0836 | 1965057.3351 | 3007836.4913 | 4054547.5918 | 5105216.8494 | 5867434.1248 | 6632565.8717 | 7400631.52 | 8171650.629 | 8945642.8883 | 9722628.1191 | 10502626.2745 | 11299387.2043 | 11463309.2716 | 11627971.966 | 12746170.22 | 13868691.9716 | 15631509.6239 | 17401093.401 | 19177488.4103 | 15203047.7524 | 16971610.4074 | 18746977.4872 | 14934538.3565 | 16902027.9114 | 18877066.612 | 15102012.4781 | 17070709.4421 | 19046963.6011 | 15921795.4803 | 18542819.0986 | 21173856.8242 | 17242323.6226 | 19053983.3583 | 20872638.4071 | 16291980.6453 | 17472828.3688 | 18658297.4089 | 14090726.2666 | 15263939.2254 | 16441722.6024 | 11866414.5592 | 13031839.0378 | 14201782.0113 | 9618581.2954 | 10776060.4834 | 11938005.1977 | 7346752.9008 | 8517289.9059 | 9692317.7638 | 5114174.1059 | 6276682.3399 | 7443627.9017 | 2857348.0656 | 4011665.8802 | 5170366.4198 | 575786.5947 | 1721749.0872 | 2872038.6024 | 0 | 0 | 600048.5459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | ORA Surplus |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1731008.3205 | 565491.7553 | 0 | 1798891.1083 | 1798891.1083 | 1798891.1083 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493
Investor Capital
|  | Opening Balance |  |  |  |  | 0 | 926184.0836 | 1965057.3351 | 3007836.4913 | 4054547.5918 | 5105216.8494 | 5867434.1248 | 6632565.8717 | 7400631.52 | 8171650.629 | 8945642.8883 | 9722628.1191 | 10502626.2745 | 11299387.2043 | 11463309.2716 | 11627971.966 | 12746170.22 | 13868691.9716 | 15631509.6239 | 17401093.401 | 19177488.4103 | 15203047.7524 | 16971610.4074 | 18746977.4872 | 14934538.3565 | 16902027.9114 | 18877066.612 | 15102012.4781 | 17070709.4421 | 19046963.6011 | 15921795.4803 | 18542819.0986 | 21173856.8242 | 17242323.6226 | 19053983.3583 | 20872638.4071 | 16291980.6453 | 17472828.3688 | 18658297.4089 | 14090726.2666 | 15263939.2254 | 16441722.6024 | 11866414.5592 | 13031839.0378 | 14201782.0113 | 9618581.2954 | 10776060.4834 | 11938005.1977 | 7346752.9008 | 8517289.9059 | 9692317.7638 | 5114174.1059 | 6276682.3399 | 7443627.9017 | 2857348.0656 | 4011665.8802 | 5170366.4198 | 575786.5947 | 1721749.0872 | 2872038.6024 | 0 | 0 | 600048.5459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Drawdown |  |  |  |  | 926184.0836 | 1038873.2514 | 1042779.1563 | 1046711.1005 | 1050669.2576 | 762217.2754 | 765131.7469 | 768065.6483 | 771019.109 | 773992.2594 | 776985.2308 | 779998.1554 | 796760.9298 | 163922.0673 | 164662.6944 | 1118198.2541 | 1122521.7516 | 1762817.6523 | 1769583.7771 | 1776395.0093 | 0 | 1768562.655 | 1775367.0798 | 0 | 1967489.5549 | 1975038.7005 | 0 | 1968696.964 | 1976254.159 | 0 | 2621023.6183 | 2631037.7256 | 0 | 1811659.7356 | 1818655.0488 | 0 | 1180847.7235 | 1185469.0401 | 0 | 1173212.9588 | 1177783.3769 | 0 | 1165424.4786 | 1169942.9735 | 0 | 1157479.188 | 1161944.7143 | 0 | 1170537.0051 | 1175027.8579 | 0 | 1162508.234 | 1166945.5617 | 0 | 1154317.8147 | 1158700.5396 | 0 | 1145962.4925 | 1150289.5152 | 0 | 0 | 600048.5459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Repayment |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3974440.6579 | 0 | 0 | -3812439.1307 | 0 | 0 | -3775054.1339 | 0 | 0 | -3125168.1209 | 0 | 0 | -3931533.2015 | 0 | 0 | -4580657.7618 | 0 | 0 | -4567571.1423 | 0 | 0 | -4575308.0431 | 0 | 0 | -4583200.7159 | 0 | 0 | -4591252.2969 | 0 | 0 | -4578143.6579 | 0 | 0 | -4586279.8361 | 0 | 0 | -4594579.8251 | 0 | 0 | -2872038.6024 | 0 | 0 | -600048.5459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Closing Balance |  |  |  |  | 926184.0836 | 1965057.3351 | 3007836.4913 | 4054547.5918 | 5105216.8494 | 5867434.1248 | 6632565.8717 | 7400631.52 | 8171650.629 | 8945642.8883 | 9722628.1191 | 10502626.2745 | 11299387.2043 | 11463309.2716 | 11627971.966 | 12746170.22 | 13868691.9716 | 15631509.6239 | 17401093.401 | 19177488.4103 | 15203047.7524 | 16971610.4074 | 18746977.4872 | 14934538.3565 | 16902027.9114 | 18877066.612 | 15102012.4781 | 17070709.4421 | 19046963.6011 | 15921795.4803 | 18542819.0986 | 21173856.8242 | 17242323.6226 | 19053983.3583 | 20872638.4071 | 16291980.6453 | 17472828.3688 | 18658297.4089 | 14090726.2666 | 15263939.2254 | 16441722.6024 | 11866414.5592 | 13031839.0378 | 14201782.0113 | 9618581.2954 | 10776060.4834 | 11938005.1977 | 7346752.9008 | 8517289.9059 | 9692317.7638 | 5114174.1059 | 6276682.3399 | 7443627.9017 | 2857348.0656 | 4011665.8802 | 5170366.4198 | 575786.5947 | 1721749.0872 | 2872038.6024 | 0 | 0 | 600048.5459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Preferred Interest
|  | Opening Balance |  |  |  |  | 0 | 0 | 2701.3702 | 8440.6665 | 17238.1415 | 29114.1832 | 44089.3154 | 61331.2588 | 80855.1254 | 102676.1281 | 126809.5812 | 153270.9009 | 182075.6063 | 213239.3202 | 246817.8142 | 280972.3515 | 315706.7725 | 353803.9137 | 395286.1933 | 442031.0145 | 494073.4607 | 551448.8495 | 597399.4646 | 648642.41 | 705212.9681 | 750828.9094 | 802316.4085 | 859714.609 | 906269.6463 | 958702.502 | 1017052.3614 | 1066457.3343 | 1123651.0572 | 1188685.4552 | 1242442.565 | 1301640.474 | 1366315.4541 | 1417818.8177 | 1472916.5386 | 1531632.5793 | 1577197.7926 | 1626317.7756 | 1679016.2267 | 1718523.7332 | 1761545.6246 | 1808105.3302 | 1841433.1662 | 1878234.1893 | 1918531.5542 | 1945555.3005 | 1976071.9324 | 2010104.7356 | 2030883.8823 | 2055114.2837 | 2082818.9485 | 2097227.7689 | 2115045.3754 | 2136294.4931 | 2144204.7296 | 2155480.4283 | 2170144.0254 | 2176473.6122 | 2182821.6602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Preferred Interest | 8% |  |  |  | 0 | 6174.5606 | 13118.3914 | 20108.5144 | 27145.2382 | 34228.8736 | 39410.1563 | 44625.9809 | 49876.5776 | 55162.1784 | 60483.0165 | 65839.3268 | 71231.3459 | 76750.8435 | 78067.5139 | 79392.9621 | 87079.1799 | 94816.6392 | 106845.3054 | 118954.1628 | 131143.7458 | 105029.9773 | 117126.7325 | 129304.1326 | 104265.0088 | 117685.7121 | 131195.8868 | 106411.5139 | 119846.5273 | 133371.1074 | 112925.6523 | 130728.5096 | 148650.0525 | 122873.3939 | 135309.5062 | 147828.5259 | 117721.974 | 125937.6479 | 134208.093 | 104149.059 | 112274.2468 | 120453.6025 | 90302.8719 | 98335.7518 | 106422.1842 | 76177.9108 | 84116.6243 | 92108.2626 | 61768.563 | 69752.3014 | 77789.2646 | 47495.1923 | 55383.7748 | 63324.9479 | 32934.4468 | 40725.9577 | 48569.412 | 18080.5406 | 25773.0254 | 33516.7935 | 14467.6268 | 14509.8241 | 18552.468 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Paid - Periodic | 4.5% |  |  |  | 0 | -3473.1903 | -7379.0951 | -11311.0393 | -15269.1965 | -19253.7414 | -22168.2129 | -25102.1142 | -28055.5749 | -31028.7253 | -34021.6968 | -37034.6213 | -40067.6321 | -43172.3495 | -43912.9766 | -44658.5412 | -48982.0387 | -53334.3596 | -60100.4843 | -66911.7166 | -73768.357 | -59079.3623 | -65883.787 | -72733.5746 | -58649.0675 | -66198.2131 | -73797.6863 | -59856.4766 | -67413.6716 | -75021.2479 | -63520.6794 | -73534.7866 | -83615.6546 | -69116.284 | -76111.5972 | -83153.5458 | -66218.6104 | -70839.9269 | -75492.0523 | -58583.8457 | -63154.2638 | -67755.1514 | -50795.3654 | -55313.8604 | -59862.4786 | -42850.0748 | -47315.6012 | -51810.8977 | -34744.8167 | -39235.6695 | -43756.4614 | -26716.0457 | -31153.3733 | -35620.2832 | -18525.6263 | -22908.3512 | -27320.2942 | -10170.3041 | -14497.3268 | -18853.1964 | -8138.0401 | -8161.776 | -10435.7633 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Paid - Balance |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2190938.365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Closing Balance |  |  |  |  | 0 | 2701.3702 | 8440.6665 | 17238.1415 | 29114.1832 | 44089.3154 | 61331.2588 | 80855.1254 | 102676.1281 | 126809.5812 | 153270.9009 | 182075.6063 | 213239.3202 | 246817.8142 | 280972.3515 | 315706.7725 | 353803.9137 | 395286.1933 | 442031.0145 | 494073.4607 | 551448.8495 | 597399.4646 | 648642.41 | 705212.9681 | 750828.9094 | 802316.4085 | 859714.609 | 906269.6463 | 958702.502 | 1017052.3614 | 1066457.3343 | 1123651.0572 | 1188685.4552 | 1242442.565 | 1301640.474 | 1366315.4541 | 1417818.8177 | 1472916.5386 | 1531632.5793 | 1577197.7926 | 1626317.7756 | 1679016.2267 | 1718523.7332 | 1761545.6246 | 1808105.3302 | 1841433.1662 | 1878234.1893 | 1918531.5542 | 1945555.3005 | 1976071.9324 | 2010104.7356 | 2030883.8823 | 2055114.2837 | 2082818.9485 | 2097227.7689 | 2115045.3754 | 2136294.4931 | 2144204.7296 | 2155480.4283 | 2170144.0254 | 2176473.6122 | 2182821.6602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Terminal Value |  |  |  |  | 2041-05-31: 0
ORA Surplus
|  | Opening Balance |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1731008.3205 | 565491.7553 | 0 | 1798891.1083 | 1798891.1083 | 1798891.1083 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493
|  | Increase |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1731008.3205 | 0 | 0 | 1798891.1083 | 0 | 0 | 959615.3846 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Decrease |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1165516.5653 | -565491.7553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Closing Balance |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1731008.3205 | 565491.7553 | 0 | 1798891.1083 | 1798891.1083 | 1798891.1083 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493 | 2758506.493
OPERATING
|  | Unit Turnover Scaling |  |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 100% | 20% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 60% | 60% | 60% | 60% | 60% | 60% | 60% | 60% | 60% | 60% | 60% | 60% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Total Value (ORA Sales) | 87325000
|  | Average Tenure | 8 | years
|  | Average DMF | 15%
|  | Resale Fee | 1%
|  | Terminal Discount Rate | 17.5%
Operating Cashflows
|  | Unit Turnover Income |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28120.708 | 28120.708 | 28120.708 | 28120.708 | 28120.708 | 28120.708 | 28120.708 | 28120.708 | 28120.708 | 28683.1222 | 143415.611 | 28683.1222 | 57366.2444 | 57366.2444 | 57366.2444 | 57366.2444 | 57366.2444 | 57366.2444 | 57366.2444 | 57366.2444 | 57366.2444 | 58513.5693 | 58513.5693 | 58513.5693 | 87770.3539 | 87770.3539 | 87770.3539 | 87770.3539 | 87770.3539 | 87770.3539 | 87770.3539 | 87770.3539 | 87770.3539 | 89525.761 | 89525.761 | 89525.761 | 119367.6814 | 119367.6814 | 119367.6814 | 119367.6814 | 119367.6814 | 119367.6814 | 119367.6814 | 119367.6814 | 119367.6814 | 121755.035 | 121755.035 | 121755.035 | 152193.7937 | 152193.7937 | 152193.7937 | 152193.7937 | 152193.7937 | 152193.7937 | 152193.7937 | 152193.7937 | 152193.7937 | 155237.6696 | 155237.6696 | 155237.6696 | 155237.6696 | 155237.6696 | 155237.6696 | 155237.6696 | 155237.6696 | 155237.6696 | 155237.6696 | 155237.6696 | 155237.6696 | 158342.423 | 158342.423 | 158342.423 | 158342.423 | 158342.423 | 158342.423 | 158342.423 | 158342.423 | 158342.423 | 158342.423 | 158342.423 | 158342.423 | 161509.2715 | 161509.2715 | 161509.2715 | 161509.2715 | 161509.2715 | 161509.2715 | 161509.2715 | 161509.2715 | 161509.2715 | 161509.2715 | 161509.2715 | 161509.2715 | 164739.4569 | 164739.4569 | 164739.4569 | 164739.4569 | 164739.4569 | 164739.4569 | 164739.4569 | 164739.4569 | 164739.4569 | 164739.4569 | 164739.4569 | 164739.4569 | 168034.246 | 168034.246 | 168034.246 | 168034.246 | 168034.246 | 168034.246 | 168034.246 | 168034.246 | 168034.246 | 168034.246 | 168034.246 | 168034.246
|  | Ground Lease | -56475.35 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -62353.3498 | -62353.3498 | -62353.3498 | -62353.3498 | -62353.3498 | -62353.3498 | -62353.3498 | -62353.3498 | -62353.3498 | -63600.4168 | -63600.4168 | -63600.4168 | -63600.4168 | -63600.4168 | -63600.4168 | -63600.4168 | -63600.4168 | -63600.4168 | -63600.4168 | -63600.4168 | -63600.4168 | -64872.4251 | -64872.4251 | -64872.4251 | -64872.4251 | -64872.4251 | -64872.4251 | -64872.4251 | -64872.4251 | -64872.4251 | -64872.4251 | -64872.4251 | -64872.4251 | -66169.8736 | -66169.8736 | -66169.8736 | -66169.8736 | -66169.8736 | -66169.8736 | -66169.8736 | -66169.8736 | -66169.8736 | -66169.8736 | -66169.8736 | -66169.8736 | -67493.2711 | -67493.2711 | -67493.2711 | -67493.2711 | -67493.2711 | -67493.2711 | -67493.2711 | -67493.2711 | -67493.2711 | -67493.2711 | -67493.2711 | -67493.2711 | -68843.1365 | -68843.1365 | -68843.1365 | -68843.1365 | -68843.1365 | -68843.1365 | -68843.1365 | -68843.1365 | -68843.1365 | -68843.1365 | -68843.1365 | -68843.1365 | -70219.9992 | -70219.9992 | -70219.9992 | -70219.9992 | -70219.9992 | -70219.9992 | -70219.9992 | -70219.9992 | -70219.9992 | -70219.9992 | -70219.9992 | -70219.9992 | -71624.3992 | -71624.3992 | -71624.3992 | -71624.3992 | -71624.3992 | -71624.3992 | -71624.3992 | -71624.3992 | -71624.3992 | -71624.3992 | -71624.3992 | -71624.3992 | -73056.8872 | -73056.8872 | -73056.8872 | -73056.8872 | -73056.8872 | -73056.8872 | -73056.8872 | -73056.8872 | -73056.8872 | -73056.8872 | -73056.8872 | -73056.8872 | -74518.025 | -74518.025 | -74518.025 | -74518.025 | -74518.025 | -74518.025 | -74518.025 | -74518.025 | -74518.025 | -74518.025 | -74518.025 | -74518.025
|  | Terminal Value |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6412540.8725
|  | Net Operating Cashflows |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -34232.6417 | -34232.6417 | -34232.6417 | -34232.6417 | -34232.6417 | -34232.6417 | -34232.6417 | -34232.6417 | -34232.6417 | -34917.2946 | 79815.1942 | -34917.2946 | -6234.1724 | -6234.1724 | -6234.1724 | -6234.1724 | -6234.1724 | -6234.1724 | -6234.1724 | -6234.1724 | -6234.1724 | -6358.8558 | -6358.8558 | -6358.8558 | 22897.9288 | 22897.9288 | 22897.9288 | 22897.9288 | 22897.9288 | 22897.9288 | 22897.9288 | 22897.9288 | 22897.9288 | 23355.8874 | 23355.8874 | 23355.8874 | 53197.8077 | 53197.8077 | 53197.8077 | 53197.8077 | 53197.8077 | 53197.8077 | 53197.8077 | 53197.8077 | 53197.8077 | 54261.7639 | 54261.7639 | 54261.7639 | 84700.5226 | 84700.5226 | 84700.5226 | 84700.5226 | 84700.5226 | 84700.5226 | 84700.5226 | 84700.5226 | 84700.5226 | 86394.5331 | 86394.5331 | 86394.5331 | 86394.5331 | 86394.5331 | 86394.5331 | 86394.5331 | 86394.5331 | 86394.5331 | 86394.5331 | 86394.5331 | 86394.5331 | 88122.4237 | 88122.4237 | 88122.4237 | 88122.4237 | 88122.4237 | 88122.4237 | 88122.4237 | 88122.4237 | 88122.4237 | 88122.4237 | 88122.4237 | 88122.4237 | 89884.8722 | 89884.8722 | 89884.8722 | 89884.8722 | 89884.8722 | 89884.8722 | 89884.8722 | 89884.8722 | 89884.8722 | 89884.8722 | 89884.8722 | 89884.8722 | 91682.5697 | 91682.5697 | 91682.5697 | 91682.5697 | 91682.5697 | 91682.5697 | 91682.5697 | 91682.5697 | 91682.5697 | 91682.5697 | 91682.5697 | 91682.5697 | 93516.2211 | 93516.2211 | 93516.2211 | 93516.2211 | 93516.2211 | 93516.2211 | 93516.2211 | 93516.2211 | 93516.2211 | 93516.2211 | 93516.2211 | 6506057.0936
SHARE CLASS SUMMARY
A-Class
|  | Investor Capital |  |  |  |  | -926184.0836 | -1038873.2514 | -1042779.1563 | -1046711.1005 | -1050669.2576 | -762217.2754 | -765131.7469 | -768065.6483 | -771019.109 | -773992.2594 | -776985.2308 | -779998.1554 | -796760.9298 | -163922.0673 | -164662.6944 | -1118198.2541 | -1122521.7516 | -1762817.6523 | -1769583.7771 | -1776395.0093 | 3974440.6579 | -1768562.655 | -1775367.0798 | 3812439.1307 | -1967489.5549 | -1975038.7005 | 3775054.1339 | -1968696.964 | -1976254.159 | 3125168.1209 | -2621023.6183 | -2631037.7256 | 3931533.2015 | -1811659.7356 | -1818655.0488 | 4580657.7618 | -1180847.7235 | -1185469.0401 | 4567571.1423 | -1173212.9588 | -1177783.3769 | 4575308.0431 | -1165424.4786 | -1169942.9735 | 4583200.7159 | -1157479.188 | -1161944.7143 | 4591252.2969 | -1170537.0051 | -1175027.8579 | 4578143.6579 | -1162508.234 | -1166945.5617 | 4586279.8361 | -1154317.8147 | -1158700.5396 | 4594579.8251 | -1145962.4925 | -1150289.5152 | 2872038.6024 | 0 | -600048.5459 | 600048.5459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Preferred Interest |  |  |  |  | 0 | 3473.1903 | 7379.0951 | 11311.0393 | 15269.1965 | 19253.7414 | 22168.2129 | 25102.1142 | 28055.5749 | 31028.7253 | 34021.6968 | 37034.6213 | 40067.6321 | 43172.3495 | 43912.9766 | 44658.5412 | 48982.0387 | 53334.3596 | 60100.4843 | 66911.7166 | 73768.357 | 59079.3623 | 65883.787 | 72733.5746 | 58649.0675 | 66198.2131 | 73797.6863 | 59856.4766 | 67413.6716 | 75021.2479 | 63520.6794 | 73534.7866 | 83615.6546 | 69116.284 | 76111.5972 | 83153.5458 | 66218.6104 | 70839.9269 | 75492.0523 | 58583.8457 | 63154.2638 | 67755.1514 | 50795.3654 | 55313.8604 | 59862.4786 | 42850.0748 | 47315.6012 | 51810.8977 | 34744.8167 | 39235.6695 | 43756.4614 | 26716.0457 | 31153.3733 | 35620.2832 | 18525.6263 | 22908.3512 | 27320.2942 | 10170.3041 | 14497.3268 | 18853.1964 | 8138.0401 | 8161.776 | 2201374.1283 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Share of ORA Surplus | 70% |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1211705.8244 | -815861.5957 | -395844.2287 | 1259223.7758 | 0 | 0 | 671730.7692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Share of Operating Cashflows | 70% |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -23962.8492 | -23962.8492 | -23962.8492 | -23962.8492 | -23962.8492 | -23962.8492 | -23962.8492 | -23962.8492 | -23962.8492 | -24442.1062 | 55870.636 | -24442.1062 | -4363.9207 | -4363.9207 | -4363.9207 | -4363.9207 | -4363.9207 | -4363.9207 | -4363.9207 | -4363.9207 | -4363.9207 | -4451.1991 | -4451.1991 | -4451.1991 | 16028.5502 | 16028.5502 | 16028.5502 | 16028.5502 | 16028.5502 | 16028.5502 | 16028.5502 | 16028.5502 | 16028.5502 | 16349.1212 | 16349.1212 | 16349.1212 | 37238.4654 | 37238.4654 | 37238.4654 | 37238.4654 | 37238.4654 | 37238.4654 | 37238.4654 | 37238.4654 | 37238.4654 | 37983.2347 | 37983.2347 | 37983.2347 | 59290.3658 | 59290.3658 | 59290.3658 | 59290.3658 | 59290.3658 | 59290.3658 | 59290.3658 | 59290.3658 | 59290.3658 | 60476.1732 | 60476.1732 | 60476.1732 | 60476.1732 | 60476.1732 | 60476.1732 | 60476.1732 | 60476.1732 | 60476.1732 | 60476.1732 | 60476.1732 | 60476.1732 | 61685.6966 | 61685.6966 | 61685.6966 | 61685.6966 | 61685.6966 | 61685.6966 | 61685.6966 | 61685.6966 | 61685.6966 | 61685.6966 | 61685.6966 | 61685.6966 | 62919.4106 | 62919.4106 | 62919.4106 | 62919.4106 | 62919.4106 | 62919.4106 | 62919.4106 | 62919.4106 | 62919.4106 | 62919.4106 | 62919.4106 | 62919.4106 | 64177.7988 | 64177.7988 | 64177.7988 | 64177.7988 | 64177.7988 | 64177.7988 | 64177.7988 | 64177.7988 | 64177.7988 | 64177.7988 | 64177.7988 | 64177.7988 | 65461.3547 | 65461.3547 | 65461.3547 | 65461.3547 | 65461.3547 | 65461.3547 | 65461.3547 | 65461.3547 | 65461.3547 | 65461.3547 | 65461.3547 | 4554239.9655
|  | Net Cashflow |  |  |  |  | -926184.0836 | -1035400.0611 | -1035400.0611 | -1035400.0611 | -1035400.0611 | -742963.534 | -742963.534 | -742963.534 | -742963.534 | -742963.534 | -742963.534 | -742963.534 | -756693.2977 | -120749.7178 | -120749.7178 | -1073539.7129 | -1073539.7129 | -1709483.2928 | -1709483.2928 | -1709483.2928 | 4048209.0149 | -1709483.2928 | -1709483.2928 | 3885172.7053 | -1908840.4875 | -1908840.4875 | 3848851.8202 | -1908840.4875 | -1908840.4875 | 3200189.3688 | -2557502.9389 | -2557502.9389 | 4015148.8561 | -1742543.4516 | -1742543.4516 | 4663811.3076 | -1114629.1131 | -1114629.1131 | 4643063.1946 | -1114629.1131 | -1114629.1131 | 4643063.1946 | -1114629.1131 | -1114629.1131 | 4643063.1946 | -1114629.1131 | -1114629.1131 | 4643063.1946 | -1135792.1884 | -1135792.1884 | 4621900.1193 | -1135792.1884 | -1135792.1884 | 4621900.1193 | -1135792.1884 | -1135792.1884 | 4621900.1193 | -1135792.1884 | -1135792.1884 | 4102597.6231 | -807723.5556 | -987730.9986 | 4060646.45 | -23962.8492 | -23962.8492 | 647767.92 | -23962.8492 | -23962.8492 | -23962.8492 | -23962.8492 | -23962.8492 | -23962.8492 | -24442.1062 | 55870.636 | -24442.1062 | -4363.9207 | -4363.9207 | -4363.9207 | -4363.9207 | -4363.9207 | -4363.9207 | -4363.9207 | -4363.9207 | -4363.9207 | -4451.1991 | -4451.1991 | -4451.1991 | 16028.5502 | 16028.5502 | 16028.5502 | 16028.5502 | 16028.5502 | 16028.5502 | 16028.5502 | 16028.5502 | 16028.5502 | 16349.1212 | 16349.1212 | 16349.1212 | 37238.4654 | 37238.4654 | 37238.4654 | 37238.4654 | 37238.4654 | 37238.4654 | 37238.4654 | 37238.4654 | 37238.4654 | 37983.2347 | 37983.2347 | 37983.2347 | 59290.3658 | 59290.3658 | 59290.3658 | 59290.3658 | 59290.3658 | 59290.3658 | 59290.3658 | 59290.3658 | 59290.3658 | 60476.1732 | 60476.1732 | 60476.1732 | 60476.1732 | 60476.1732 | 60476.1732 | 60476.1732 | 60476.1732 | 60476.1732 | 60476.1732 | 60476.1732 | 60476.1732 | 61685.6966 | 61685.6966 | 61685.6966 | 61685.6966 | 61685.6966 | 61685.6966 | 61685.6966 | 61685.6966 | 61685.6966 | 61685.6966 | 61685.6966 | 61685.6966 | 62919.4106 | 62919.4106 | 62919.4106 | 62919.4106 | 62919.4106 | 62919.4106 | 62919.4106 | 62919.4106 | 62919.4106 | 62919.4106 | 62919.4106 | 62919.4106 | 64177.7988 | 64177.7988 | 64177.7988 | 64177.7988 | 64177.7988 | 64177.7988 | 64177.7988 | 64177.7988 | 64177.7988 | 64177.7988 | 64177.7988 | 64177.7988 | 65461.3547 | 65461.3547 | 65461.3547 | 65461.3547 | 65461.3547 | 65461.3547 | 65461.3547 | 65461.3547 | 65461.3547 | 65461.3547 | 65461.3547 | 4554239.9655
B-Class
|  | Share of ORA Surplus | 30% |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 519302.4962 | -349654.9696 | -169647.5266 | 539667.3325 | 0 | 0 | 287884.6154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Share of Operating Cashflows | 30% |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -10269.7925 | -10269.7925 | -10269.7925 | -10269.7925 | -10269.7925 | -10269.7925 | -10269.7925 | -10269.7925 | -10269.7925 | -10475.1884 | 23944.5583 | -10475.1884 | -1870.2517 | -1870.2517 | -1870.2517 | -1870.2517 | -1870.2517 | -1870.2517 | -1870.2517 | -1870.2517 | -1870.2517 | -1907.6567 | -1907.6567 | -1907.6567 | 6869.3786 | 6869.3786 | 6869.3786 | 6869.3786 | 6869.3786 | 6869.3786 | 6869.3786 | 6869.3786 | 6869.3786 | 7006.7662 | 7006.7662 | 7006.7662 | 15959.3423 | 15959.3423 | 15959.3423 | 15959.3423 | 15959.3423 | 15959.3423 | 15959.3423 | 15959.3423 | 15959.3423 | 16278.5292 | 16278.5292 | 16278.5292 | 25410.1568 | 25410.1568 | 25410.1568 | 25410.1568 | 25410.1568 | 25410.1568 | 25410.1568 | 25410.1568 | 25410.1568 | 25918.3599 | 25918.3599 | 25918.3599 | 25918.3599 | 25918.3599 | 25918.3599 | 25918.3599 | 25918.3599 | 25918.3599 | 25918.3599 | 25918.3599 | 25918.3599 | 26436.7271 | 26436.7271 | 26436.7271 | 26436.7271 | 26436.7271 | 26436.7271 | 26436.7271 | 26436.7271 | 26436.7271 | 26436.7271 | 26436.7271 | 26436.7271 | 26965.4617 | 26965.4617 | 26965.4617 | 26965.4617 | 26965.4617 | 26965.4617 | 26965.4617 | 26965.4617 | 26965.4617 | 26965.4617 | 26965.4617 | 26965.4617 | 27504.7709 | 27504.7709 | 27504.7709 | 27504.7709 | 27504.7709 | 27504.7709 | 27504.7709 | 27504.7709 | 27504.7709 | 27504.7709 | 27504.7709 | 27504.7709 | 28054.8663 | 28054.8663 | 28054.8663 | 28054.8663 | 28054.8663 | 28054.8663 | 28054.8663 | 28054.8663 | 28054.8663 | 28054.8663 | 28054.8663 | 1951817.1281
|  | Net Cashflow |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 519302.4962 | -349654.9696 | -169647.5266 | 539667.3325 | -10269.7925 | -10269.7925 | 277614.8229 | -10269.7925 | -10269.7925 | -10269.7925 | -10269.7925 | -10269.7925 | -10269.7925 | -10475.1884 | 23944.5583 | -10475.1884 | -1870.2517 | -1870.2517 | -1870.2517 | -1870.2517 | -1870.2517 | -1870.2517 | -1870.2517 | -1870.2517 | -1870.2517 | -1907.6567 | -1907.6567 | -1907.6567 | 6869.3786 | 6869.3786 | 6869.3786 | 6869.3786 | 6869.3786 | 6869.3786 | 6869.3786 | 6869.3786 | 6869.3786 | 7006.7662 | 7006.7662 | 7006.7662 | 15959.3423 | 15959.3423 | 15959.3423 | 15959.3423 | 15959.3423 | 15959.3423 | 15959.3423 | 15959.3423 | 15959.3423 | 16278.5292 | 16278.5292 | 16278.5292 | 25410.1568 | 25410.1568 | 25410.1568 | 25410.1568 | 25410.1568 | 25410.1568 | 25410.1568 | 25410.1568 | 25410.1568 | 25918.3599 | 25918.3599 | 25918.3599 | 25918.3599 | 25918.3599 | 25918.3599 | 25918.3599 | 25918.3599 | 25918.3599 | 25918.3599 | 25918.3599 | 25918.3599 | 26436.7271 | 26436.7271 | 26436.7271 | 26436.7271 | 26436.7271 | 26436.7271 | 26436.7271 | 26436.7271 | 26436.7271 | 26436.7271 | 26436.7271 | 26436.7271 | 26965.4617 | 26965.4617 | 26965.4617 | 26965.4617 | 26965.4617 | 26965.4617 | 26965.4617 | 26965.4617 | 26965.4617 | 26965.4617 | 26965.4617 | 26965.4617 | 27504.7709 | 27504.7709 | 27504.7709 | 27504.7709 | 27504.7709 | 27504.7709 | 27504.7709 | 27504.7709 | 27504.7709 | 27504.7709 | 27504.7709 | 27504.7709 | 28054.8663 | 28054.8663 | 28054.8663 | 28054.8663 | 28054.8663 | 28054.8663 | 28054.8663 | 28054.8663 | 28054.8663 | 28054.8663 | 28054.8663 | 1951817.1281
PARTNER SUMMARY
Hāpai
|  | Share of A-Class | 100% |  |  |  | -926184.0836 | -1035400.0611 | -1035400.0611 | -1035400.0611 | -1035400.0611 | -742963.534 | -742963.534 | -742963.534 | -742963.534 | -742963.534 | -742963.534 | -742963.534 | -756693.2977 | -120749.7178 | -120749.7178 | -1073539.7129 | -1073539.7129 | -1709483.2928 | -1709483.2928 | -1709483.2928 | 4048209.0149 | -1709483.2928 | -1709483.2928 | 3885172.7053 | -1908840.4875 | -1908840.4875 | 3848851.8202 | -1908840.4875 | -1908840.4875 | 3200189.3688 | -2557502.9389 | -2557502.9389 | 4015148.8561 | -1742543.4516 | -1742543.4516 | 4663811.3076 | -1114629.1131 | -1114629.1131 | 4643063.1946 | -1114629.1131 | -1114629.1131 | 4643063.1946 | -1114629.1131 | -1114629.1131 | 4643063.1946 | -1114629.1131 | -1114629.1131 | 4643063.1946 | -1135792.1884 | -1135792.1884 | 4621900.1193 | -1135792.1884 | -1135792.1884 | 4621900.1193 | -1135792.1884 | -1135792.1884 | 4621900.1193 | -1135792.1884 | -1135792.1884 | 4102597.6231 | -807723.5556 | -987730.9986 | 4060646.45 | -23962.8492 | -23962.8492 | 647767.92 | -23962.8492 | -23962.8492 | -23962.8492 | -23962.8492 | -23962.8492 | -23962.8492 | -24442.1062 | 55870.636 | -24442.1062 | -4363.9207 | -4363.9207 | -4363.9207 | -4363.9207 | -4363.9207 | -4363.9207 | -4363.9207 | -4363.9207 | -4363.9207 | -4451.1991 | -4451.1991 | -4451.1991 | 16028.5502 | 16028.5502 | 16028.5502 | 16028.5502 | 16028.5502 | 16028.5502 | 16028.5502 | 16028.5502 | 16028.5502 | 16349.1212 | 16349.1212 | 16349.1212 | 37238.4654 | 37238.4654 | 37238.4654 | 37238.4654 | 37238.4654 | 37238.4654 | 37238.4654 | 37238.4654 | 37238.4654 | 37983.2347 | 37983.2347 | 37983.2347 | 59290.3658 | 59290.3658 | 59290.3658 | 59290.3658 | 59290.3658 | 59290.3658 | 59290.3658 | 59290.3658 | 59290.3658 | 60476.1732 | 60476.1732 | 60476.1732 | 60476.1732 | 60476.1732 | 60476.1732 | 60476.1732 | 60476.1732 | 60476.1732 | 60476.1732 | 60476.1732 | 60476.1732 | 61685.6966 | 61685.6966 | 61685.6966 | 61685.6966 | 61685.6966 | 61685.6966 | 61685.6966 | 61685.6966 | 61685.6966 | 61685.6966 | 61685.6966 | 61685.6966 | 62919.4106 | 62919.4106 | 62919.4106 | 62919.4106 | 62919.4106 | 62919.4106 | 62919.4106 | 62919.4106 | 62919.4106 | 62919.4106 | 62919.4106 | 62919.4106 | 64177.7988 | 64177.7988 | 64177.7988 | 64177.7988 | 64177.7988 | 64177.7988 | 64177.7988 | 64177.7988 | 64177.7988 | 64177.7988 | 64177.7988 | 64177.7988 | 65461.3547 | 65461.3547 | 65461.3547 | 65461.3547 | 65461.3547 | 65461.3547 | 65461.3547 | 65461.3547 | 65461.3547 | 65461.3547 | 65461.3547 | 4554239.9655
|  | Share of B-Class | 50% |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 259651.2481 | -174827.4848 | -84823.7633 | 269833.6663 | -5134.8963 | -5134.8963 | 138807.4114 | -5134.8963 | -5134.8963 | -5134.8963 | -5134.8963 | -5134.8963 | -5134.8963 | -5237.5942 | 11972.2791 | -5237.5942 | -935.1259 | -935.1259 | -935.1259 | -935.1259 | -935.1259 | -935.1259 | -935.1259 | -935.1259 | -935.1259 | -953.8284 | -953.8284 | -953.8284 | 3434.6893 | 3434.6893 | 3434.6893 | 3434.6893 | 3434.6893 | 3434.6893 | 3434.6893 | 3434.6893 | 3434.6893 | 3503.3831 | 3503.3831 | 3503.3831 | 7979.6712 | 7979.6712 | 7979.6712 | 7979.6712 | 7979.6712 | 7979.6712 | 7979.6712 | 7979.6712 | 7979.6712 | 8139.2646 | 8139.2646 | 8139.2646 | 12705.0784 | 12705.0784 | 12705.0784 | 12705.0784 | 12705.0784 | 12705.0784 | 12705.0784 | 12705.0784 | 12705.0784 | 12959.18 | 12959.18 | 12959.18 | 12959.18 | 12959.18 | 12959.18 | 12959.18 | 12959.18 | 12959.18 | 12959.18 | 12959.18 | 12959.18 | 13218.3636 | 13218.3636 | 13218.3636 | 13218.3636 | 13218.3636 | 13218.3636 | 13218.3636 | 13218.3636 | 13218.3636 | 13218.3636 | 13218.3636 | 13218.3636 | 13482.7308 | 13482.7308 | 13482.7308 | 13482.7308 | 13482.7308 | 13482.7308 | 13482.7308 | 13482.7308 | 13482.7308 | 13482.7308 | 13482.7308 | 13482.7308 | 13752.3854 | 13752.3854 | 13752.3854 | 13752.3854 | 13752.3854 | 13752.3854 | 13752.3854 | 13752.3854 | 13752.3854 | 13752.3854 | 13752.3854 | 13752.3854 | 14027.4332 | 14027.4332 | 14027.4332 | 14027.4332 | 14027.4332 | 14027.4332 | 14027.4332 | 14027.4332 | 14027.4332 | 14027.4332 | 14027.4332 | 975908.564
|  | Net Cashflow |  |  |  |  | -926184.0836 | -1035400.0611 | -1035400.0611 | -1035400.0611 | -1035400.0611 | -742963.534 | -742963.534 | -742963.534 | -742963.534 | -742963.534 | -742963.534 | -742963.534 | -756693.2977 | -120749.7178 | -120749.7178 | -1073539.7129 | -1073539.7129 | -1709483.2928 | -1709483.2928 | -1709483.2928 | 4048209.0149 | -1709483.2928 | -1709483.2928 | 3885172.7053 | -1908840.4875 | -1908840.4875 | 3848851.8202 | -1908840.4875 | -1908840.4875 | 3200189.3688 | -2557502.9389 | -2557502.9389 | 4015148.8561 | -1742543.4516 | -1742543.4516 | 4663811.3076 | -1114629.1131 | -1114629.1131 | 4643063.1946 | -1114629.1131 | -1114629.1131 | 4643063.1946 | -1114629.1131 | -1114629.1131 | 4643063.1946 | -1114629.1131 | -1114629.1131 | 4643063.1946 | -1135792.1884 | -1135792.1884 | 4621900.1193 | -1135792.1884 | -1135792.1884 | 4621900.1193 | -1135792.1884 | -1135792.1884 | 4621900.1193 | -1135792.1884 | -1135792.1884 | 4362248.8712 | -982551.0404 | -1072554.7619 | 4330480.1163 | -29097.7455 | -29097.7455 | 786575.3314 | -29097.7455 | -29097.7455 | -29097.7455 | -29097.7455 | -29097.7455 | -29097.7455 | -29679.7004 | 67842.9151 | -29679.7004 | -5299.0465 | -5299.0465 | -5299.0465 | -5299.0465 | -5299.0465 | -5299.0465 | -5299.0465 | -5299.0465 | -5299.0465 | -5405.0275 | -5405.0275 | -5405.0275 | 19463.2395 | 19463.2395 | 19463.2395 | 19463.2395 | 19463.2395 | 19463.2395 | 19463.2395 | 19463.2395 | 19463.2395 | 19852.5043 | 19852.5043 | 19852.5043 | 45218.1366 | 45218.1366 | 45218.1366 | 45218.1366 | 45218.1366 | 45218.1366 | 45218.1366 | 45218.1366 | 45218.1366 | 46122.4993 | 46122.4993 | 46122.4993 | 71995.4442 | 71995.4442 | 71995.4442 | 71995.4442 | 71995.4442 | 71995.4442 | 71995.4442 | 71995.4442 | 71995.4442 | 73435.3531 | 73435.3531 | 73435.3531 | 73435.3531 | 73435.3531 | 73435.3531 | 73435.3531 | 73435.3531 | 73435.3531 | 73435.3531 | 73435.3531 | 73435.3531 | 74904.0602 | 74904.0602 | 74904.0602 | 74904.0602 | 74904.0602 | 74904.0602 | 74904.0602 | 74904.0602 | 74904.0602 | 74904.0602 | 74904.0602 | 74904.0602 | 76402.1414 | 76402.1414 | 76402.1414 | 76402.1414 | 76402.1414 | 76402.1414 | 76402.1414 | 76402.1414 | 76402.1414 | 76402.1414 | 76402.1414 | 76402.1414 | 77930.1842 | 77930.1842 | 77930.1842 | 77930.1842 | 77930.1842 | 77930.1842 | 77930.1842 | 77930.1842 | 77930.1842 | 77930.1842 | 77930.1842 | 77930.1842 | 79488.7879 | 79488.7879 | 79488.7879 | 79488.7879 | 79488.7879 | 79488.7879 | 79488.7879 | 79488.7879 | 79488.7879 | 79488.7879 | 79488.7879 | 5530148.5295
KPV
|  | Share of A-Class | 0% |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Share of B-Class | 50% |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 259651.2481 | -174827.4848 | -84823.7633 | 269833.6663 | -5134.8963 | -5134.8963 | 138807.4114 | -5134.8963 | -5134.8963 | -5134.8963 | -5134.8963 | -5134.8963 | -5134.8963 | -5237.5942 | 11972.2791 | -5237.5942 | -935.1259 | -935.1259 | -935.1259 | -935.1259 | -935.1259 | -935.1259 | -935.1259 | -935.1259 | -935.1259 | -953.8284 | -953.8284 | -953.8284 | 3434.6893 | 3434.6893 | 3434.6893 | 3434.6893 | 3434.6893 | 3434.6893 | 3434.6893 | 3434.6893 | 3434.6893 | 3503.3831 | 3503.3831 | 3503.3831 | 7979.6712 | 7979.6712 | 7979.6712 | 7979.6712 | 7979.6712 | 7979.6712 | 7979.6712 | 7979.6712 | 7979.6712 | 8139.2646 | 8139.2646 | 8139.2646 | 12705.0784 | 12705.0784 | 12705.0784 | 12705.0784 | 12705.0784 | 12705.0784 | 12705.0784 | 12705.0784 | 12705.0784 | 12959.18 | 12959.18 | 12959.18 | 12959.18 | 12959.18 | 12959.18 | 12959.18 | 12959.18 | 12959.18 | 12959.18 | 12959.18 | 12959.18 | 13218.3636 | 13218.3636 | 13218.3636 | 13218.3636 | 13218.3636 | 13218.3636 | 13218.3636 | 13218.3636 | 13218.3636 | 13218.3636 | 13218.3636 | 13218.3636 | 13482.7308 | 13482.7308 | 13482.7308 | 13482.7308 | 13482.7308 | 13482.7308 | 13482.7308 | 13482.7308 | 13482.7308 | 13482.7308 | 13482.7308 | 13482.7308 | 13752.3854 | 13752.3854 | 13752.3854 | 13752.3854 | 13752.3854 | 13752.3854 | 13752.3854 | 13752.3854 | 13752.3854 | 13752.3854 | 13752.3854 | 13752.3854 | 14027.4332 | 14027.4332 | 14027.4332 | 14027.4332 | 14027.4332 | 14027.4332 | 14027.4332 | 14027.4332 | 14027.4332 | 14027.4332 | 14027.4332 | 975908.564
|  | Net Cashflow |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 259651.2481 | -174827.4848 | -84823.7633 | 269833.6663 | -5134.8963 | -5134.8963 | 138807.4114 | -5134.8963 | -5134.8963 | -5134.8963 | -5134.8963 | -5134.8963 | -5134.8963 | -5237.5942 | 11972.2791 | -5237.5942 | -935.1259 | -935.1259 | -935.1259 | -935.1259 | -935.1259 | -935.1259 | -935.1259 | -935.1259 | -935.1259 | -953.8284 | -953.8284 | -953.8284 | 3434.6893 | 3434.6893 | 3434.6893 | 3434.6893 | 3434.6893 | 3434.6893 | 3434.6893 | 3434.6893 | 3434.6893 | 3503.3831 | 3503.3831 | 3503.3831 | 7979.6712 | 7979.6712 | 7979.6712 | 7979.6712 | 7979.6712 | 7979.6712 | 7979.6712 | 7979.6712 | 7979.6712 | 8139.2646 | 8139.2646 | 8139.2646 | 12705.0784 | 12705.0784 | 12705.0784 | 12705.0784 | 12705.0784 | 12705.0784 | 12705.0784 | 12705.0784 | 12705.0784 | 12959.18 | 12959.18 | 12959.18 | 12959.18 | 12959.18 | 12959.18 | 12959.18 | 12959.18 | 12959.18 | 12959.18 | 12959.18 | 12959.18 | 13218.3636 | 13218.3636 | 13218.3636 | 13218.3636 | 13218.3636 | 13218.3636 | 13218.3636 | 13218.3636 | 13218.3636 | 13218.3636 | 13218.3636 | 13218.3636 | 13482.7308 | 13482.7308 | 13482.7308 | 13482.7308 | 13482.7308 | 13482.7308 | 13482.7308 | 13482.7308 | 13482.7308 | 13482.7308 | 13482.7308 | 13482.7308 | 13752.3854 | 13752.3854 | 13752.3854 | 13752.3854 | 13752.3854 | 13752.3854 | 13752.3854 | 13752.3854 | 13752.3854 | 13752.3854 | 13752.3854 | 13752.3854 | 14027.4332 | 14027.4332 | 14027.4332 | 14027.4332 | 14027.4332 | 14027.4332 | 14027.4332 | 14027.4332 | 14027.4332 | 14027.4332 | 14027.4332 | 975908.564
Vendor
|  | Share of A-Class | 0% |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Share of B-Class | 0% |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Net Cashflow |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Combined
|  | Hāpai |  |  |  |  | -926184.0836 | -1035400.0611 | -1035400.0611 | -1035400.0611 | -1035400.0611 | -742963.534 | -742963.534 | -742963.534 | -742963.534 | -742963.534 | -742963.534 | -742963.534 | -756693.2977 | -120749.7178 | -120749.7178 | -1073539.7129 | -1073539.7129 | -1709483.2928 | -1709483.2928 | -1709483.2928 | 4048209.0149 | -1709483.2928 | -1709483.2928 | 3885172.7053 | -1908840.4875 | -1908840.4875 | 3848851.8202 | -1908840.4875 | -1908840.4875 | 3200189.3688 | -2557502.9389 | -2557502.9389 | 4015148.8561 | -1742543.4516 | -1742543.4516 | 4663811.3076 | -1114629.1131 | -1114629.1131 | 4643063.1946 | -1114629.1131 | -1114629.1131 | 4643063.1946 | -1114629.1131 | -1114629.1131 | 4643063.1946 | -1114629.1131 | -1114629.1131 | 4643063.1946 | -1135792.1884 | -1135792.1884 | 4621900.1193 | -1135792.1884 | -1135792.1884 | 4621900.1193 | -1135792.1884 | -1135792.1884 | 4621900.1193 | -1135792.1884 | -1135792.1884 | 4362248.8712 | -982551.0404 | -1072554.7619 | 4330480.1163 | -29097.7455 | -29097.7455 | 786575.3314 | -29097.7455 | -29097.7455 | -29097.7455 | -29097.7455 | -29097.7455 | -29097.7455 | -29679.7004 | 67842.9151 | -29679.7004 | -5299.0465 | -5299.0465 | -5299.0465 | -5299.0465 | -5299.0465 | -5299.0465 | -5299.0465 | -5299.0465 | -5299.0465 | -5405.0275 | -5405.0275 | -5405.0275 | 19463.2395 | 19463.2395 | 19463.2395 | 19463.2395 | 19463.2395 | 19463.2395 | 19463.2395 | 19463.2395 | 19463.2395 | 19852.5043 | 19852.5043 | 19852.5043 | 45218.1366 | 45218.1366 | 45218.1366 | 45218.1366 | 45218.1366 | 45218.1366 | 45218.1366 | 45218.1366 | 45218.1366 | 46122.4993 | 46122.4993 | 46122.4993 | 71995.4442 | 71995.4442 | 71995.4442 | 71995.4442 | 71995.4442 | 71995.4442 | 71995.4442 | 71995.4442 | 71995.4442 | 73435.3531 | 73435.3531 | 73435.3531 | 73435.3531 | 73435.3531 | 73435.3531 | 73435.3531 | 73435.3531 | 73435.3531 | 73435.3531 | 73435.3531 | 73435.3531 | 74904.0602 | 74904.0602 | 74904.0602 | 74904.0602 | 74904.0602 | 74904.0602 | 74904.0602 | 74904.0602 | 74904.0602 | 74904.0602 | 74904.0602 | 74904.0602 | 76402.1414 | 76402.1414 | 76402.1414 | 76402.1414 | 76402.1414 | 76402.1414 | 76402.1414 | 76402.1414 | 76402.1414 | 76402.1414 | 76402.1414 | 76402.1414 | 77930.1842 | 77930.1842 | 77930.1842 | 77930.1842 | 77930.1842 | 77930.1842 | 77930.1842 | 77930.1842 | 77930.1842 | 77930.1842 | 77930.1842 | 77930.1842 | 79488.7879 | 79488.7879 | 79488.7879 | 79488.7879 | 79488.7879 | 79488.7879 | 79488.7879 | 79488.7879 | 79488.7879 | 79488.7879 | 79488.7879 | 5530148.5295
|  | KPV |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 259651.2481 | -174827.4848 | -84823.7633 | 269833.6663 | -5134.8963 | -5134.8963 | 138807.4114 | -5134.8963 | -5134.8963 | -5134.8963 | -5134.8963 | -5134.8963 | -5134.8963 | -5237.5942 | 11972.2791 | -5237.5942 | -935.1259 | -935.1259 | -935.1259 | -935.1259 | -935.1259 | -935.1259 | -935.1259 | -935.1259 | -935.1259 | -953.8284 | -953.8284 | -953.8284 | 3434.6893 | 3434.6893 | 3434.6893 | 3434.6893 | 3434.6893 | 3434.6893 | 3434.6893 | 3434.6893 | 3434.6893 | 3503.3831 | 3503.3831 | 3503.3831 | 7979.6712 | 7979.6712 | 7979.6712 | 7979.6712 | 7979.6712 | 7979.6712 | 7979.6712 | 7979.6712 | 7979.6712 | 8139.2646 | 8139.2646 | 8139.2646 | 12705.0784 | 12705.0784 | 12705.0784 | 12705.0784 | 12705.0784 | 12705.0784 | 12705.0784 | 12705.0784 | 12705.0784 | 12959.18 | 12959.18 | 12959.18 | 12959.18 | 12959.18 | 12959.18 | 12959.18 | 12959.18 | 12959.18 | 12959.18 | 12959.18 | 12959.18 | 13218.3636 | 13218.3636 | 13218.3636 | 13218.3636 | 13218.3636 | 13218.3636 | 13218.3636 | 13218.3636 | 13218.3636 | 13218.3636 | 13218.3636 | 13218.3636 | 13482.7308 | 13482.7308 | 13482.7308 | 13482.7308 | 13482.7308 | 13482.7308 | 13482.7308 | 13482.7308 | 13482.7308 | 13482.7308 | 13482.7308 | 13482.7308 | 13752.3854 | 13752.3854 | 13752.3854 | 13752.3854 | 13752.3854 | 13752.3854 | 13752.3854 | 13752.3854 | 13752.3854 | 13752.3854 | 13752.3854 | 13752.3854 | 14027.4332 | 14027.4332 | 14027.4332 | 14027.4332 | 14027.4332 | 14027.4332 | 14027.4332 | 14027.4332 | 14027.4332 | 14027.4332 | 14027.4332 | 975908.564
|  | Vendor |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Net Cashflow |  |  |  |  | -926184.0836 | -1035400.0611 | -1035400.0611 | -1035400.0611 | -1035400.0611 | -742963.534 | -742963.534 | -742963.534 | -742963.534 | -742963.534 | -742963.534 | -742963.534 | -756693.2977 | -120749.7178 | -120749.7178 | -1073539.7129 | -1073539.7129 | -1709483.2928 | -1709483.2928 | -1709483.2928 | 4048209.0149 | -1709483.2928 | -1709483.2928 | 3885172.7053 | -1908840.4875 | -1908840.4875 | 3848851.8202 | -1908840.4875 | -1908840.4875 | 3200189.3688 | -2557502.9389 | -2557502.9389 | 4015148.8561 | -1742543.4516 | -1742543.4516 | 4663811.3076 | -1114629.1131 | -1114629.1131 | 4643063.1946 | -1114629.1131 | -1114629.1131 | 4643063.1946 | -1114629.1131 | -1114629.1131 | 4643063.1946 | -1114629.1131 | -1114629.1131 | 4643063.1946 | -1135792.1884 | -1135792.1884 | 4621900.1193 | -1135792.1884 | -1135792.1884 | 4621900.1193 | -1135792.1884 | -1135792.1884 | 4621900.1193 | -1135792.1884 | -1135792.1884 | 4621900.1193 | -1157378.5252 | -1157378.5252 | 4600313.7825 | -34232.6417 | -34232.6417 | 925382.7429 | -34232.6417 | -34232.6417 | -34232.6417 | -34232.6417 | -34232.6417 | -34232.6417 | -34917.2946 | 79815.1942 | -34917.2946 | -6234.1724 | -6234.1724 | -6234.1724 | -6234.1724 | -6234.1724 | -6234.1724 | -6234.1724 | -6234.1724 | -6234.1724 | -6358.8558 | -6358.8558 | -6358.8558 | 22897.9288 | 22897.9288 | 22897.9288 | 22897.9288 | 22897.9288 | 22897.9288 | 22897.9288 | 22897.9288 | 22897.9288 | 23355.8874 | 23355.8874 | 23355.8874 | 53197.8077 | 53197.8077 | 53197.8077 | 53197.8077 | 53197.8077 | 53197.8077 | 53197.8077 | 53197.8077 | 53197.8077 | 54261.7639 | 54261.7639 | 54261.7639 | 84700.5226 | 84700.5226 | 84700.5226 | 84700.5226 | 84700.5226 | 84700.5226 | 84700.5226 | 84700.5226 | 84700.5226 | 86394.5331 | 86394.5331 | 86394.5331 | 86394.5331 | 86394.5331 | 86394.5331 | 86394.5331 | 86394.5331 | 86394.5331 | 86394.5331 | 86394.5331 | 86394.5331 | 88122.4237 | 88122.4237 | 88122.4237 | 88122.4237 | 88122.4237 | 88122.4237 | 88122.4237 | 88122.4237 | 88122.4237 | 88122.4237 | 88122.4237 | 88122.4237 | 89884.8722 | 89884.8722 | 89884.8722 | 89884.8722 | 89884.8722 | 89884.8722 | 89884.8722 | 89884.8722 | 89884.8722 | 89884.8722 | 89884.8722 | 89884.8722 | 91682.5697 | 91682.5697 | 91682.5697 | 91682.5697 | 91682.5697 | 91682.5697 | 91682.5697 | 91682.5697 | 91682.5697 | 91682.5697 | 91682.5697 | 91682.5697 | 93516.2211 | 93516.2211 | 93516.2211 | 93516.2211 | 93516.2211 | 93516.2211 | 93516.2211 | 93516.2211 | 93516.2211 | 93516.2211 | 93516.2211 | 6506057.0936
WORKINGS
Cumulative Partner Cashflows
|  | Hāpai |  |  |  |  | -926184.0836 | -1961584.1448 | -2996984.2059 | -4032384.267 | -5067784.3281 | -5810747.8621 | -6553711.3962 | -7296674.9302 | -8039638.4642 | -8782601.9983 | -9525565.5323 | -10268529.0663 | -11025222.3641 | -11145972.0819 | -11266721.7997 | -12340261.5126 | -13413801.2255 | -15123284.5182 | -16832767.811 | -18542251.1037 | -14494042.0888 | -16203525.3815 | -17913008.6743 | -14027835.969 | -15936676.4564 | -17845516.9439 | -13996665.1237 | -15905505.6111 | -17814346.0986 | -14614156.7298 | -17171659.6688 | -19729162.6077 | -15714013.7516 | -17456557.2032 | -19199100.6548 | -14535289.3473 | -15649918.4604 | -16764547.5735 | -12121484.3789 | -13236113.4921 | -14350742.6052 | -9707679.4106 | -10822308.5238 | -11936937.6369 | -7293874.4423 | -8408503.5555 | -9523132.6686 | -4880069.474 | -6015861.6624 | -7151653.8508 | -2529753.7315 | -3665545.9199 | -4801338.1083 | -179437.989 | -1315230.1774 | -2451022.3657 | 2170877.7536 | 1035085.5652 | -100706.6232 | 4261542.248 | 3278991.2076 | 2206436.4458 | 6536916.5621 | 6507818.8166 | 6478721.0711 | 7265296.4025 | 7236198.657 | 7207100.9115 | 7178003.1661 | 7148905.4206 | 7119807.6751 | 7090709.9296 | 7061030.2292 | 7128873.1443 | 7099193.4439 | 7093894.3974 | 7088595.3508 | 7083296.3043 | 7077997.2578 | 7072698.2113 | 7067399.1647 | 7062100.1182 | 7056801.0717 | 7051502.0252 | 7046096.9977 | 7040691.9703 | 7035286.9428 | 7054750.1823 | 7074213.4218 | 7093676.6613 | 7113139.9008 | 7132603.1403 | 7152066.3798 | 7171529.6193 | 7190992.8588 | 7210456.0983 | 7230308.6025 | 7250161.1068 | 7270013.6111 | 7315231.7477 | 7360449.8842 | 7405668.0208 | 7450886.1574 | 7496104.294 | 7541322.4305 | 7586540.5671 | 7631758.7037 | 7676976.8402 | 7723099.3395 | 7769221.8388 | 7815344.3382 | 7887339.7824 | 7959335.2266 | 8031330.6709 | 8103326.1151 | 8175321.5593 | 8247317.0036 | 8319312.4478 | 8391307.892 | 8463303.3363 | 8536738.6894 | 8610174.0425 | 8683609.3956 | 8757044.7488 | 8830480.1019 | 8903915.455 | 8977350.8081 | 9050786.1612 | 9124221.5144 | 9197656.8675 | 9271092.2206 | 9344527.5737 | 9419431.6339 | 9494335.6941 | 9569239.7543 | 9644143.8145 | 9719047.8746 | 9793951.9348 | 9868855.995 | 9943760.0552 | 10018664.1154 | 10093568.1756 | 10168472.2357 | 10243376.2959 | 10319778.4373 | 10396180.5787 | 10472582.7201 | 10548984.8615 | 10625387.0029 | 10701789.1442 | 10778191.2856 | 10854593.427 | 10930995.5684 | 11007397.7098 | 11083799.8512 | 11160201.9926 | 11238132.1768 | 11316062.361 | 11393992.5452 | 11471922.7294 | 11549852.9136 | 11627783.0979 | 11705713.2821 | 11783643.4663 | 11861573.6505 | 11939503.8347 | 12017434.0189 | 12095364.2031 | 12174852.991 | 12254341.7789 | 12333830.5668 | 12413319.3547 | 12492808.1426 | 12572296.9305 | 12651785.7184 | 12731274.5063 | 12810763.2942 | 12890252.0821 | 12969740.87 | 18499889.3996
|  | KPV |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 259651.2481 | 84823.7633 | 0 | 269833.6663 | 264698.77 | 259563.8737 | 398371.2852 | 393236.3889 | 388101.4926 | 382966.5964 | 377831.7001 | 372696.8038 | 367561.9076 | 362324.3134 | 374296.5925 | 369058.9983 | 368123.8725 | 367188.7466 | 366253.6208 | 365318.4949 | 364383.3691 | 363448.2432 | 362513.1173 | 361577.9915 | 360642.8656 | 359689.0373 | 358735.2089 | 357781.3805 | 361216.0698 | 364650.7591 | 368085.4485 | 371520.1378 | 374954.8271 | 378389.5164 | 381824.2058 | 385258.8951 | 388693.5844 | 392196.9675 | 395700.3506 | 399203.7337 | 407183.4049 | 415163.0761 | 423142.7472 | 431122.4184 | 439102.0895 | 447081.7607 | 455061.4318 | 463041.103 | 471020.7742 | 479160.0388 | 487299.3033 | 495438.5679 | 508143.6463 | 520848.7247 | 533553.8031 | 546258.8815 | 558963.9599 | 571669.0383 | 584374.1167 | 597079.1951 | 609784.2735 | 622743.4534 | 635702.6334 | 648661.8134 | 661620.9933 | 674580.1733 | 687539.3532 | 700498.5332 | 713457.7132 | 726416.8931 | 739376.0731 | 752335.2531 | 765294.433 | 778512.7966 | 791731.1601 | 804949.5237 | 818167.8873 | 831386.2508 | 844604.6144 | 857822.9779 | 871041.3415 | 884259.7051 | 897478.0686 | 910696.4322 | 923914.7958 | 937397.5266 | 950880.2574 | 964362.9883 | 977845.7191 | 991328.4499 | 1004811.1808 | 1018293.9116 | 1031776.6424 | 1045259.3733 | 1058742.1041 | 1072224.8349 | 1085707.5658 | 1099459.9512 | 1113212.3367 | 1126964.7221 | 1140717.1076 | 1154469.493 | 1168221.8785 | 1181974.2639 | 1195726.6494 | 1209479.0348 | 1223231.4202 | 1236983.8057 | 1250736.1911 | 1264763.6243 | 1278791.0575 | 1292818.4906 | 1306845.9238 | 1320873.3569 | 1334900.7901 | 1348928.2233 | 1362955.6564 | 1376983.0896 | 1391010.5227 | 1405037.9559 | 2380946.5199
|  | Vendor |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total |  |  |  |  | -926184.0836 | -1961584.1448 | -2996984.2059 | -4032384.267 | -5067784.3281 | -5810747.8621 | -6553711.3962 | -7296674.9302 | -8039638.4642 | -8782601.9983 | -9525565.5323 | -10268529.0663 | -11025222.3641 | -11145972.0819 | -11266721.7997 | -12340261.5126 | -13413801.2255 | -15123284.5182 | -16832767.811 | -18542251.1037 | -14494042.0888 | -16203525.3815 | -17913008.6743 | -14027835.969 | -15936676.4564 | -17845516.9439 | -13996665.1237 | -15905505.6111 | -17814346.0986 | -14614156.7298 | -17171659.6688 | -19729162.6077 | -15714013.7516 | -17456557.2032 | -19199100.6548 | -14535289.3473 | -15649918.4604 | -16764547.5735 | -12121484.3789 | -13236113.4921 | -14350742.6052 | -9707679.4106 | -10822308.5238 | -11936937.6369 | -7293874.4423 | -8408503.5555 | -9523132.6686 | -4880069.474 | -6015861.6624 | -7151653.8508 | -2529753.7315 | -3665545.9199 | -4801338.1083 | -179437.989 | -1315230.1774 | -2451022.3657 | 2170877.7536 | 1035085.5652 | -100706.6232 | 4521193.4961 | 3363814.9709 | 2206436.4458 | 6806750.2283 | 6772517.5866 | 6738284.9448 | 7663667.6877 | 7629435.0459 | 7595202.4042 | 7560969.7624 | 7526737.1207 | 7492504.4789 | 7458271.8372 | 7423354.5426 | 7503169.7368 | 7468252.4422 | 7462018.2699 | 7455784.0975 | 7449549.9251 | 7443315.7527 | 7437081.5803 | 7430847.4079 | 7424613.2356 | 7418379.0632 | 7412144.8908 | 7405786.035 | 7399427.1791 | 7393068.3233 | 7415966.2521 | 7438864.1809 | 7461762.1098 | 7484660.0386 | 7507557.9674 | 7530455.8962 | 7553353.825 | 7576251.7538 | 7599149.6827 | 7622505.57 | 7645861.4574 | 7669217.3448 | 7722415.1526 | 7775612.9603 | 7828810.768 | 7882008.5758 | 7935206.3835 | 7988404.1912 | 8041601.999 | 8094799.8067 | 8147997.6144 | 8202259.3783 | 8256521.1422 | 8310782.9061 | 8395483.4287 | 8480183.9513 | 8564884.474 | 8649584.9966 | 8734285.5192 | 8818986.0419 | 8903686.5645 | 8988387.0871 | 9073087.6097 | 9159482.1428 | 9245876.6759 | 9332271.209 | 9418665.7421 | 9505060.2752 | 9591454.8082 | 9677849.3413 | 9764243.8744 | 9850638.4075 | 9937032.9406 | 10023427.4737 | 10109822.0067 | 10197944.4305 | 10286066.8542 | 10374189.278 | 10462311.7017 | 10550434.1255 | 10638556.5492 | 10726678.973 | 10814801.3967 | 10902923.8204 | 10991046.2442 | 11079168.6679 | 11167291.0917 | 11257175.9639 | 11347060.8361 | 11436945.7083 | 11526830.5806 | 11616715.4528 | 11706600.325 | 11796485.1972 | 11886370.0694 | 11976254.9417 | 12066139.8139 | 12156024.6861 | 12245909.5583 | 12337592.128 | 12429274.6976 | 12520957.2673 | 12612639.837 | 12704322.4066 | 12796004.9763 | 12887687.546 | 12979370.1156 | 13071052.6853 | 13162735.255 | 13254417.8246 | 13346100.3943 | 13439616.6153 | 13533132.8364 | 13626649.0575 | 13720165.2785 | 13813681.4996 | 13907197.7206 | 14000713.9417 | 14094230.1627 | 14187746.3838 | 14281262.6049 | 14374778.8259 | 20880835.9195
| Cumulative Units Complete | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 6 | 12 | 12 | 12 | 18 | 18 | 18 | 24 | 24 | 24 | 30 | 30 | 30 | 36 | 36 | 36 | 42 | 42 | 42 | 48 | 48 | 48 | 54 | 54 | 54 | 60 | 60 | 60 | 66 | 66 | 66 | 72 | 72 | 72 | 78 | 78 | 78 | 84 | 84 | 84 | 90 | 90 | 90 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91
COPY AND PASTE FOR MODELLING: Cumulative Partner Cashflows
|  | Hāpai - Freehold |  |  |  |  | -18017040.4547 | -18531794.2191 | -19046547.9834 | -19561301.7477 | -20076055.5121 | -20773198.4462 | -21470341.3803 | -22167484.3144 | -22864627.2485 | -23561770.1826 | -24258913.1168 | -24950508.2382 | -25655935.262 | -26361362.2858 | -27713798.6863 | -29066235.0869 | -29771662.1107 | -31858350.1751 | -27499457.4314 | -28939136.119 | -31025824.1834 | -25932679.7759 | -26638106.7997 | -28991183.1582 | -24945740.2358 | -26685928.5573 | -29086066.443 | -25040623.5206 | -26780811.842 | -29929886.4248 | -26633380.1996 | -29122505.2182 | -31250927.0439 | -26184831.3643 | -26904366.9286 | -28283852.0571 | -23245346.0801 | -23979272.3557 | -25386347.1868 | -20347841.2099 | -21081767.4854 | -22488842.3165 | -17450336.3396 | -18184262.6152 | -19591337.4463 | -14552831.4693 | -15286757.7449 | -16693832.576 | -11683468.0956 | -12432072.8967 | -13867289.2244 | -8856924.7441 | -9605529.5452 | -11040745.8729 | -6030381.3925 | -6778986.1936 | -8214202.5213 | -3203838.041 | -3952442.8421 | -5387659.1698 | -405999.016 | -1169575.9131 | -2633496.5674 | 2348163.5864 | 1584586.6893 | 120666.035 | 5102326.1888 | 4338749.2917 | 2874828.6374 | 7619088.0769 | 6972792.5094 | 6326504.9476 | 11884356.8732 | 12062514.3309 | 12098145.8225 | 16516772.2635 | 16552403.755 | 16588035.2466 | 16623666.7381 | 16659298.2297 | 16694929.7212 | 16730561.2127 | 16766192.7043 | 16801824.1958 | 16838168.3172 | 16910856.5599 | 16983544.8027 | 17056233.0454 | 17128921.2882 | 17201609.5309 | 17274297.7736 | 17346986.0164 | 17419674.2591 | 17492362.5019 | 17565050.7446 | 17637738.9873 | 17711880.9949 | 17823094.0063 | 17934307.0177 | 18045520.0291 | 18156733.0405 | 18267946.0519 | 18379159.0633 | 18490372.0747 | 18601585.0861 | 18712798.0975 | 18824011.1089 | 18935224.1203 | 19048661.3919 | 19199911.0874 | 19351160.7829 | 19502410.4784 | 19653660.1739 | 19804909.8693 | 19956159.5648 | 20107409.2603 | 20258658.9558 | 20409908.6513 | 20561158.3468 | 20712408.0423 | 20866682.7317 | 21059526.0935 | 21252369.4552 | 21445212.817 | 21638056.1787 | 21830899.5405 | 22023742.9023 | 22216586.264 | 22409429.6258 | 22602272.9875 | 22795116.3493 | 22987959.711 | 23184659.94 | 23381360.169 | 23578060.398 | 23774760.627 | 23971460.856 | 24168161.085 | 24364861.314 | 24561561.543 | 24758261.7719 | 24954962.0009 | 25151662.2299 | 25348362.4589 | 25548996.6925 | 25749630.9261 | 25950265.1596 | 26150899.3932 | 26351533.6268 | 26552167.8603 | 26752802.0939 | 26953436.3275 | 27154070.5611 | 27354704.7946 | 27555339.0282 | 27755973.2618 | 27960620.18 | 28165267.0982 | 28369914.0165 | 28574560.9347 | 28779207.853 | 28983854.7712 | 29188501.6895 | 29393148.6077 | 29597795.5259 | 29802442.4442 | 30007089.3624 | 30211736.2807 | 30420476.1373 | 30629215.9939 | 30837955.8505 | 31046695.7071 | 31255435.5637 | 31464175.4203 | 31672915.2769 | 31881655.1335 | 32090394.9901 | 32299134.8467 | 32507874.7033 | 47030204.7273
|  | KPV - Freehold |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 237400.7144 | 120119.3847 | 2830.0494 | 111710.4967 | 143150.0481 | 149437.9584 | 929195.5656 | 935483.4759 | 941771.3862 | 948059.2964 | 954347.2067 | 960635.117 | 966923.0272 | 973210.9375 | 979498.8478 | 985912.5163 | 998739.8532 | 1011567.1902 | 1024394.5271 | 1037221.8641 | 1050049.201 | 1062876.538 | 1075703.8749 | 1088531.2119 | 1101358.5488 | 1114185.8858 | 1127013.2228 | 1140097.1065 | 1159722.932 | 1179348.7575 | 1198974.5831 | 1218600.4086 | 1238226.2342 | 1257852.0597 | 1277477.8852 | 1297103.7108 | 1316729.5363 | 1336355.3619 | 1355981.1874 | 1375999.5294 | 1402690.6522 | 1429381.7749 | 1456072.8976 | 1482764.0204 | 1509455.1431 | 1536146.2658 | 1562837.3886 | 1589528.5113 | 1616219.6341 | 1642910.7568 | 1669601.8795 | 1696826.8247 | 1730858.0062 | 1764889.1877 | 1798920.3692 | 1832951.5507 | 1866982.7321 | 1901013.9136 | 1935045.0951 | 1969076.2766 | 2003107.4581 | 2037138.6396 | 2071169.8211 | 2105881.6262 | 2140593.4313 | 2175305.2364 | 2210017.0415 | 2244728.8466 | 2279440.6518 | 2314152.4569 | 2348864.262 | 2383576.0671 | 2418287.8722 | 2452999.6773 | 2487711.4824 | 2523117.5237 | 2558523.5649 | 2593929.6061 | 2629335.6473 | 2664741.6885 | 2700147.7298 | 2735553.771 | 2770959.8122 | 2806365.8534 | 2841771.8946 | 2877177.9358 | 2912583.9771 | 2948698.1391 | 2984812.3012 | 3020926.4632 | 3057040.6252 | 3093154.7873 | 3129268.9493 | 3165383.1114 | 3201497.2734 | 3237611.4355 | 3273725.5975 | 3309839.7595 | 3345953.9216 | 3382790.3669 | 3419626.8121 | 3456463.2574 | 3493299.7027 | 3530136.148 | 3566972.5933 | 3603809.0386 | 3640645.4838 | 3677481.9291 | 3714318.3744 | 3751154.8197 | 6313918.9416
|  | Vendor - Freehold |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total |  |  |  |  | -18017040.4547 | -18531794.2191 | -19046547.9834 | -19561301.7477 | -20076055.5121 | -20773198.4462 | -21470341.3803 | -22167484.3144 | -22864627.2485 | -23561770.1826 | -24258913.1168 | -24950508.2382 | -25655935.262 | -26361362.2858 | -27713798.6863 | -29066235.0869 | -29771662.1107 | -31858350.1751 | -27499457.4314 | -28939136.119 | -31025824.1834 | -25932679.7759 | -26638106.7997 | -28991183.1582 | -24945740.2358 | -26685928.5573 | -29086066.443 | -25040623.5206 | -26780811.842 | -29929886.4248 | -26633380.1996 | -29122505.2182 | -31250927.0439 | -26184831.3643 | -26904366.9286 | -28283852.0571 | -23245346.0801 | -23979272.3557 | -25386347.1868 | -20347841.2099 | -21081767.4854 | -22488842.3165 | -17450336.3396 | -18184262.6152 | -19591337.4463 | -14552831.4693 | -15286757.7449 | -16693832.576 | -11683468.0956 | -12432072.8967 | -13867289.2244 | -8856924.7441 | -9605529.5452 | -11040745.8729 | -6030381.3925 | -6778986.1936 | -8214202.5213 | -3203838.041 | -3952442.8421 | -5387659.1698 | -405999.016 | -1169575.9131 | -2633496.5674 | 2348163.5864 | 1584586.6893 | 120666.035 | 5102326.1888 | 4338749.2917 | 2874828.6374 | 7856488.7912 | 7092911.8941 | 6329334.997 | 11996067.37 | 12205664.379 | 12247583.7808 | 17445967.8291 | 17487887.2309 | 17529806.6327 | 17571726.0345 | 17613645.4364 | 17655564.8382 | 17697484.24 | 17739403.6418 | 17781323.0436 | 17824080.8335 | 17909596.4131 | 17995111.9928 | 18080627.5725 | 18166143.1522 | 18251658.7319 | 18337174.3116 | 18422689.8913 | 18508205.471 | 18593721.0507 | 18679236.6304 | 18764752.2101 | 18851978.1014 | 18982816.9383 | 19113655.7752 | 19244494.6122 | 19375333.4491 | 19506172.286 | 19637011.123 | 19767849.9599 | 19898688.7968 | 20029527.6338 | 20160366.4707 | 20291205.3076 | 20424660.9213 | 20602601.7395 | 20780542.5578 | 20958483.376 | 21136424.1942 | 21314365.0125 | 21492305.8307 | 21670246.6489 | 21848187.4671 | 22026128.2854 | 22204069.1036 | 22382009.9218 | 22563509.5564 | 22790384.0997 | 23017258.6429 | 23244133.1862 | 23471007.7294 | 23697882.2726 | 23924756.8159 | 24151631.3591 | 24378505.9024 | 24605380.4456 | 24832254.9888 | 25059129.5321 | 25290541.5662 | 25521953.6003 | 25753365.6344 | 25984777.6685 | 26216189.7026 | 26447601.7367 | 26679013.7708 | 26910425.8049 | 27141837.839 | 27373249.8732 | 27604661.9073 | 27836073.9414 | 28072114.2162 | 28308154.4909 | 28544194.7657 | 28780235.0405 | 29016275.3153 | 29252315.5901 | 29488355.8649 | 29724396.1397 | 29960436.4145 | 30196476.6893 | 30432516.964 | 30668557.2388 | 30909318.3191 | 31150079.3994 | 31390840.4797 | 31631601.56 | 31872362.6403 | 32113123.7205 | 32353884.8008 | 32594645.8811 | 32835406.9614 | 33076168.0417 | 33316929.122 | 33557690.2022 | 33803266.5041 | 34048842.806 | 34294419.1079 | 34539995.4098 | 34785571.7117 | 35031148.0136 | 35276724.3155 | 35522300.6174 | 35767876.9193 | 36013453.2211 | 36259029.523 | 53344123.6688
COPY AND PASTE FOR MODELLING: Cumulative Partner Cashflows
|  | Hāpai - Ground Lease |  |  |  |  | -1159148.4797 | -1758615.2691 | -2358082.0584 | -2957548.8477 | -3557015.6371 | -4338871.5962 | -5120727.5553 | -5902583.5144 | -6684439.4735 | -7466295.4326 | -8248151.3918 | -9024459.5382 | -9814599.587 | -10604739.6358 | -12041889.0613 | -13479038.4869 | -14269178.5357 | -16440579.6251 | -12166399.9064 | -13690791.619 | -15862192.7084 | -10853761.3259 | -11643901.3747 | -14081690.7582 | -10120960.8608 | -11945862.2073 | -14430713.118 | -10469983.2206 | -12294884.567 | -15528672.1748 | -12316878.9746 | -14890717.0182 | -17103851.8689 | -12122469.2143 | -12926717.8036 | -14390915.9571 | -9437123.0051 | -10255762.3057 | -11747550.1618 | -6793757.2099 | -7612396.5104 | -9104184.3665 | -4150391.4146 | -4969030.7152 | -6460818.5713 | -1507025.6193 | -2325664.9199 | -3817452.776 | 1108198.6794 | 274880.8533 | -1245048.4994 | 3429302.7135 | 2721859.8661 | 1327355.7771 | 5618873.8617 | 4911439.8445 | 3620388.6143 | 7808083.663 | 7100657.4221 | 5809613.9909 | 9972918.1838 | 9252773.5058 | 7937339.2645 | 12100651.3477 | 11380514.5832 | 10065088.2783 | 14228408.3212 | 13508279.5395 | 12192861.2407 | 16356189.3131 | 15636068.5843 | 14915950.5555 | 19910619.0705 | 20007685.9968 | 19962226.9569 | 24299762.8665 | 24254303.8267 | 24208844.7868 | 24163385.7469 | 24117926.7071 | 24072467.6672 | 24027008.6274 | 23981549.5875 | 23936090.5476 | 23889722.327 | 23879698.2277 | 23869674.1284 | 23859650.0291 | 23849625.9298 | 23839601.8305 | 23829577.7313 | 23819553.632 | 23809529.5327 | 23799505.4334 | 23789481.3341 | 23779457.2348 | 23769232.6535 | 23796079.0761 | 23822925.4986 | 23849771.9211 | 23876618.3436 | 23903464.7662 | 23930311.1887 | 23957157.6112 | 23984004.0337 | 24010850.4563 | 24037696.8788 | 24064543.3013 | 24091926.6523 | 24157122.4271 | 24222318.202 | 24287513.9768 | 24352709.7517 | 24417905.5265 | 24483101.3014 | 24548297.0762 | 24613492.8511 | 24678688.6259 | 24743884.4008 | 24809080.1756 | 24875579.866 | 24980648.2286 | 25085716.5913 | 25190784.954 | 25295853.3167 | 25400921.6794 | 25505990.0421 | 25611058.4048 | 25716126.7675 | 25821195.1302 | 25926263.4929 | 26031331.8556 | 26138501.5856 | 26245671.3155 | 26352841.0455 | 26460010.7754 | 26567180.5054 | 26674350.2353 | 26781519.9653 | 26888689.6952 | 26995859.4252 | 27103029.1551 | 27210198.8851 | 27317368.615 | 27426681.7396 | 27535994.8641 | 27645307.9887 | 27754621.1132 | 27863934.2378 | 27973247.3623 | 28082560.4868 | 28191873.6114 | 28301186.7359 | 28410499.8605 | 28519812.985 | 28629126.1096 | 28740625.4966 | 28852124.8837 | 28963624.2707 | 29075123.6578 | 29186623.0448 | 29298122.4318 | 29409621.8189 | 29521121.2059 | 29632620.593 | 29744119.98 | 29855619.367 | 29967118.7541 | 30080848.1289 | 30194577.5036 | 30308306.8784 | 30422036.2532 | 30535765.628 | 30649495.0028 | 30763224.3775 | 30876953.7523 | 30990683.1271 | 31104412.5019 | 31218141.8767 | 39130456.9507
|  | KPV - Ground Lease |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 251300.2424 | 125425.2637 | 0 | 634133.3707 | 508249.5618 | 279371.4394 | 1017327.846 | 891436.2608 | 662550.3393 | 1396193.2752 | 1268048.031 | 1034848.5931 | 1768483.6387 | 1640330.4811 | 1407123.1067 | 2140750.1926 | 2012589.0522 | 1779373.6717 | 2512992.7281 | 2384823.5348 | 2256651.6414 | 2844002.4745 | 2861131.9321 | 2853109.7486 | 3618557.2621 | 3610535.0785 | 3602512.895 | 3594490.7115 | 3586468.528 | 3578446.3445 | 3570424.161 | 3562401.9775 | 3554379.794 | 3546197.1668 | 3544428.2081 | 3542659.2494 | 3540890.2907 | 3539121.332 | 3537352.3733 | 3535583.4146 | 3533814.456 | 3532045.4973 | 3530276.5386 | 3528507.5799 | 3526738.6212 | 3524934.2833 | 3529671.8873 | 3534409.4912 | 3539147.0952 | 3543884.6992 | 3548622.3032 | 3553359.9071 | 3558097.5111 | 3562835.1151 | 3567572.7191 | 3572310.323 | 3577047.927 | 3581880.2831 | 3593385.4198 | 3604890.5565 | 3616395.6933 | 3627900.83 | 3639405.9668 | 3650911.1035 | 3662416.2402 | 3673921.377 | 3685426.5137 | 3696931.6504 | 3708436.7872 | 3720172.0267 | 3738713.5024 | 3757254.9782 | 3775796.454 | 3794337.9297 | 3812879.4055 | 3831420.8813 | 3849962.357 | 3868503.8328 | 3887045.3086 | 3905586.7844 | 3924128.2601 | 3943040.5654 | 3961952.8707 | 3980865.176 | 3999777.4813 | 4018689.7865 | 4037602.0918 | 4056514.3971 | 4075426.7024 | 4094339.0077 | 4113251.313 | 4132163.6183 | 4151075.9235 | 4170366.4749 | 4189657.0263 | 4208947.5777 | 4228238.1291 | 4247528.6805 | 4266819.2319 | 4286109.7833 | 4305400.3347 | 4324690.8861 | 4343981.4375 | 4363271.9888 | 4382562.5402 | 4402238.9027 | 4421915.2651 | 4441591.6275 | 4461267.9899 | 4480944.3523 | 4500620.7148 | 4520297.0772 | 4539973.4396 | 4559649.802 | 4579326.1644 | 4599002.5268 | 4618678.8893 | 4638748.7789 | 4658818.6686 | 4678888.5583 | 4698958.4479 | 4719028.3376 | 4739098.2273 | 4759168.1169 | 4779238.0066 | 4799307.8963 | 4819377.7859 | 4839447.6756 | 6235738.571
|  | Vendor - Ground Lease |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total |  |  |  |  | -1159148.4797 | -1758615.2691 | -2358082.0584 | -2957548.8477 | -3557015.6371 | -4338871.5962 | -5120727.5553 | -5902583.5144 | -6684439.4735 | -7466295.4326 | -8248151.3918 | -9024459.5382 | -9814599.587 | -10604739.6358 | -12041889.0613 | -13479038.4869 | -14269178.5357 | -16440579.6251 | -12166399.9064 | -13690791.619 | -15862192.7084 | -10853761.3259 | -11643901.3747 | -14081690.7582 | -10120960.8608 | -11945862.2073 | -14430713.118 | -10469983.2206 | -12294884.567 | -15528672.1748 | -12316878.9746 | -14890717.0182 | -17103851.8689 | -12122469.2143 | -12926717.8036 | -14390915.9571 | -9437123.0051 | -10255762.3057 | -11747550.1618 | -6793757.2099 | -7612396.5104 | -9104184.3665 | -4150391.4146 | -4969030.7152 | -6460818.5713 | -1507025.6193 | -2325664.9199 | -3817452.776 | 1108198.6794 | 274880.8533 | -1245048.4994 | 3680602.9559 | 2847285.1298 | 1327355.7771 | 6253007.2325 | 5419689.4064 | 3899760.0537 | 8825411.509 | 7992093.6829 | 6472164.3302 | 11369111.459 | 10520821.5369 | 8972187.8576 | 13869134.9864 | 13020845.0643 | 11472211.385 | 16369158.5138 | 15520868.5917 | 13972234.9124 | 18869182.0412 | 18020892.1191 | 17172602.197 | 22754621.545 | 22868817.9288 | 22815336.7055 | 27918320.1286 | 27864838.9052 | 27811357.6819 | 27757876.4585 | 27704395.2351 | 27650914.0118 | 27597432.7884 | 27543951.565 | 27490470.3417 | 27435919.4938 | 27424126.4358 | 27412333.3778 | 27400540.3199 | 27388747.2619 | 27376954.2039 | 27365161.1459 | 27353368.0879 | 27341575.0299 | 27329781.9719 | 27317988.914 | 27306195.856 | 27294166.9368 | 27325750.9633 | 27357334.9898 | 27388919.0163 | 27420503.0428 | 27452087.0693 | 27483671.0958 | 27515255.1223 | 27546839.1488 | 27578423.1753 | 27610007.2018 | 27641591.2283 | 27673806.9353 | 27750507.8469 | 27827208.7585 | 27903909.6701 | 27980610.5817 | 28057311.4933 | 28134012.4049 | 28210713.3164 | 28287414.228 | 28364115.1396 | 28440816.0512 | 28517516.9628 | 28595751.8926 | 28719361.7311 | 28842971.5695 | 28966581.408 | 29090191.2465 | 29213801.0849 | 29337410.9234 | 29461020.7619 | 29584630.6003 | 29708240.4388 | 29831850.2773 | 29955460.1157 | 30081542.151 | 30207624.1862 | 30333706.2214 | 30459788.2567 | 30585870.2919 | 30711952.3271 | 30838034.3624 | 30964116.3976 | 31090198.4328 | 31216280.4681 | 31342362.5033 | 31468444.5386 | 31597048.2145 | 31725651.8904 | 31854255.5664 | 31982859.2423 | 32111462.9183 | 32240066.5942 | 32368670.2701 | 32497273.9461 | 32625877.622 | 32754481.298 | 32883084.9739 | 33011688.6498 | 33142864.3993 | 33274040.1487 | 33405215.8982 | 33536391.6477 | 33667567.3971 | 33798743.1466 | 33929918.896 | 34061094.6455 | 34192270.395 | 34323446.1444 | 34454621.8939 | 34585797.6433 | 34719596.9078 | 34853396.1722 | 34987195.4367 | 35120994.7011 | 35254793.9656 | 35388593.23 | 35522392.4945 | 35656191.7589 | 35789991.0234 | 35923790.2878 | 36057589.5523 | 45366195.5217
COPY AND PASTE FOR MODELLING: Annual Cashflows
|  | Hāpai - Freehold |  |  |  |  | -18017040.4547 | -514753.7643 | -514753.7643 | -514753.7643 | -514753.7643 | -697142.9341 | -697142.9341 | -697142.9341 | -697142.9341 | -697142.9341 | -697142.9341 | -691595.1214 | -705427.0238 | -705427.0238 | -1352436.4005 | -1352436.4005 | -705427.0238 | -2086688.0644 | 4358892.7437 | -1439678.6877 | -2086688.0644 | 5093144.4076 | -705427.0238 | -2353076.3585 | 4045442.9224 | -1740188.3215 | -2400137.8857 | 4045442.9224 | -1740188.3215 | -3149074.5828 | 3296506.2253 | -2489125.0186 | -2128421.8257 | 5066095.6796 | -719535.5643 | -1379485.1285 | 5038505.977 | -733926.2756 | -1407074.8311 | 5038505.977 | -733926.2756 | -1407074.8311 | 5038505.977 | -733926.2756 | -1407074.8311 | 5038505.977 | -733926.2756 | -1407074.8311 | 5010364.4804 | -748604.8011 | -1435216.3277 | 5010364.4804 | -748604.8011 | -1435216.3277 | 5010364.4804 | -748604.8011 | -1435216.3277 | 5010364.4804 | -748604.8011 | -1435216.3277 | 4981660.1538 | -763576.8971 | -1463920.6543 | 4981660.1538 | -763576.8971 | -1463920.6543 | 4981660.1538 | -763576.8971 | -1463920.6543 | 4744259.4395 | -646295.5675 | -646287.5618 | 5557851.9256 | 178157.4577 | 35631.4915 | 4418626.441 | 35631.4915 | 35631.4915 | 35631.4915 | 35631.4915 | 35631.4915 | 35631.4915 | 35631.4915 | 35631.4915 | 36344.1214 | 72688.2427 | 72688.2427 | 72688.2427 | 72688.2427 | 72688.2427 | 72688.2427 | 72688.2427 | 72688.2427 | 72688.2427 | 72688.2427 | 72688.2427 | 74142.0076 | 111213.0114 | 111213.0114 | 111213.0114 | 111213.0114 | 111213.0114 | 111213.0114 | 111213.0114 | 111213.0114 | 111213.0114 | 111213.0114 | 111213.0114 | 113437.2716 | 151249.6955 | 151249.6955 | 151249.6955 | 151249.6955 | 151249.6955 | 151249.6955 | 151249.6955 | 151249.6955 | 151249.6955 | 151249.6955 | 151249.6955 | 154274.6894 | 192843.3618 | 192843.3618 | 192843.3618 | 192843.3618 | 192843.3618 | 192843.3618 | 192843.3618 | 192843.3618 | 192843.3618 | 192843.3618 | 192843.3618 | 196700.229 | 196700.229 | 196700.229 | 196700.229 | 196700.229 | 196700.229 | 196700.229 | 196700.229 | 196700.229 | 196700.229 | 196700.229 | 196700.229 | 200634.2336 | 200634.2336 | 200634.2336 | 200634.2336 | 200634.2336 | 200634.2336 | 200634.2336 | 200634.2336 | 200634.2336 | 200634.2336 | 200634.2336 | 200634.2336 | 204646.9182 | 204646.9182 | 204646.9182 | 204646.9182 | 204646.9182 | 204646.9182 | 204646.9182 | 204646.9182 | 204646.9182 | 204646.9182 | 204646.9182 | 204646.9182 | 208739.8566 | 208739.8566 | 208739.8566 | 208739.8566 | 208739.8566 | 208739.8566 | 208739.8566 | 208739.8566 | 208739.8566 | 208739.8566 | 208739.8566 | 14522330.0239
|  | Hāpai - Ground Lease |  |  |  |  | -1159148.4797 | -599466.7893 | -599466.7893 | -599466.7893 | -599466.7893 | -781855.9591 | -781855.9591 | -781855.9591 | -781855.9591 | -781855.9591 | -781855.9591 | -776308.1464 | -790140.0488 | -790140.0488 | -1437149.4255 | -1437149.4255 | -790140.0488 | -2171401.0894 | 4274179.7187 | -1524391.7127 | -2171401.0894 | 5008431.3826 | -790140.0488 | -2437789.3835 | 3960729.8974 | -1824901.3465 | -2484850.9107 | 3960729.8974 | -1824901.3465 | -3233787.6078 | 3211793.2003 | -2573838.0436 | -2213134.8507 | 4981382.6546 | -804248.5893 | -1464198.1535 | 4953792.952 | -818639.3006 | -1491787.8561 | 4953792.952 | -818639.3006 | -1491787.8561 | 4953792.952 | -818639.3006 | -1491787.8561 | 4953792.952 | -818639.3006 | -1491787.8561 | 4925651.4554 | -833317.8261 | -1519929.3527 | 4674351.2129 | -707442.8474 | -1394504.089 | 4291518.0846 | -707434.0172 | -1291051.2303 | 4187695.0487 | -707426.2409 | -1291043.4313 | 4163304.1929 | -720144.6779 | -1315434.2414 | 4163312.0833 | -720136.7645 | -1315426.3049 | 4163320.0429 | -720128.7817 | -1315418.2988 | 4163328.0724 | -720120.7288 | -720118.0288 | 4994668.5149 | 97066.9263 | -45459.0399 | 4337535.9096 | -45459.0399 | -45459.0399 | -45459.0399 | -45459.0399 | -45459.0399 | -45459.0399 | -45459.0399 | -45459.0399 | -46368.2207 | -10024.0993 | -10024.0993 | -10024.0993 | -10024.0993 | -10024.0993 | -10024.0993 | -10024.0993 | -10024.0993 | -10024.0993 | -10024.0993 | -10024.0993 | -10224.5813 | 26846.4225 | 26846.4225 | 26846.4225 | 26846.4225 | 26846.4225 | 26846.4225 | 26846.4225 | 26846.4225 | 26846.4225 | 26846.4225 | 26846.4225 | 27383.351 | 65195.7748 | 65195.7748 | 65195.7748 | 65195.7748 | 65195.7748 | 65195.7748 | 65195.7748 | 65195.7748 | 65195.7748 | 65195.7748 | 65195.7748 | 66499.6903 | 105068.3627 | 105068.3627 | 105068.3627 | 105068.3627 | 105068.3627 | 105068.3627 | 105068.3627 | 105068.3627 | 105068.3627 | 105068.3627 | 105068.3627 | 107169.7299 | 107169.7299 | 107169.7299 | 107169.7299 | 107169.7299 | 107169.7299 | 107169.7299 | 107169.7299 | 107169.7299 | 107169.7299 | 107169.7299 | 107169.7299 | 109313.1245 | 109313.1245 | 109313.1245 | 109313.1245 | 109313.1245 | 109313.1245 | 109313.1245 | 109313.1245 | 109313.1245 | 109313.1245 | 109313.1245 | 109313.1245 | 111499.387 | 111499.387 | 111499.387 | 111499.387 | 111499.387 | 111499.387 | 111499.387 | 111499.387 | 111499.387 | 111499.387 | 111499.387 | 111499.387 | 113729.3748 | 113729.3748 | 113729.3748 | 113729.3748 | 113729.3748 | 113729.3748 | 113729.3748 | 113729.3748 | 113729.3748 | 113729.3748 | 113729.3748 | 7912315.074

## Output
KEY INPUTS & SENSITIVITY
A Class Share Allocation
|  | Hāpai | 100% | % of A-class shares
|  | Vendor | 0% | % of A-class shares
Land
|  | Model | Operating Lease | "Ownership" covers both freehold and pre-paid ground lease
|  |  | Per sqm | Total
|  | Value (excl GST) | 200 | 9821800
|  | Value (incl GST) | 230 | 11295070
|  | Cap Rate | 6% | only applicable to ground lease model
|  | Rental - annual (incl GST) | 677704.2
Build Cost
|  | Input Build Rate (psm) (incl GST) | 3718.6475 | base build rate (with premium applied for apartments where applicable)
| ORA Sales | [5 empty] | Area m2 | m2 Sell
|  | Base Value 2 Bedroom Units | 925000 |  |  |  | 122 | 7581.9672
|  | Base Value 3 Bedroom Units | 1012500 | all units valued in proportion to base value |  |  | 144 | 7031.25
|  | Average Value (incl GST) | 959615.3846 | average will vary based on proposed delivery mix
Growth & Inflation
|  | Capital Growth | 2% | applicable to ORA sales and unit turnover income
|  | Inflation - Costs | 2% | applicable to development costs
|  | Inflation - Lease | 2% | applicable to operating lease
ORA SURPLUS
|  | ORA Sales | 87325
|  | Inflation - ORA | 5168.0369 | increase in values during development - highlighted as separate item for transparency
92493.0369
|  | Land | 0
|  | Ground Lease | 3557.9471
|  | Preliminary Costs | 3609.5
|  | Land Development | 12285.2039
|  | Vertical Construction | 44174.5579
|  | Community Centre | 6945.638
|  | Holding & Other | 2359.495
|  | KPV Processing Fee | 1040.6159
|  | KPV Transaction Fee | 806.6946
|  | KPV Management Fee | 1575
|  | Inflation - Cost | 3203.982 | cost inflation during development - highlighted as separate item for transparency
79558.6344
|  | Surplus Pre-Preferred | 12934.4025 | 14.81%
|  | Preferred Interest | 5007.8591 | in 6 Years of Development |  |  |  |  | Preferred Interest; Ownership |  | 11251.3307 | Copy and paste for lease ORA surplus scenario
[9 empty] | Preferred Interest: Formula Driven |  | 5007.8591 | For comparison/to maintain back up
|  | ORA Surplus | 7926.5434 | 9.077%
Noting that at 50/50 investment the ORA surplus shifts directly from KPV to the Vendor as part of entering the lease
OUTPUT
|  |  | Hāpai | KPV | Vendor | Total |  | A Class | B Class
Shareholdings
|  | A-Class | 70% | 0% | 0% | 70% |  | 70% | 0%
|  | B-Class | 15% | 15% | 0% | 30% |  | 0% | 30%
|  | Total | 85% | 15% | 0% | 100% |  | 70% | 30%
Development Output
|  | Peak Capital (net of preferred) | 19729.1626 | 0 | 0 | 19729.1626 |  | 19729.1626 | 0
|  | Share of ORA Surplus | 6737.5619 | 1188.9815 | 0 | 7926.5434 |  | 5548.5804 | 2377.963
|  | Share of Preferred Interest | 5007.8591 | 0 | 0 | 5007.8591 |  | 5007.8591 | 0
|  | Total | 11745.421 | 1188.9815 | 0 | 12934.4025 |  | 10556.4395 | 2377.963
|  | Margin (on share of costs) | 14.76% | n/a | n/a | 16.26% |  | 13.27% | n/a
|  | Margin (on share of capital) | 59.53% | n/a | n/a | 65.56% |  | 53.51% | n/a
Long Term Investment
|  | IRR (15 year - real basis) | 15.38% | n/a | n/a | 16.22% |  | 14.47% | 2.98e-07%
|  | Annual Cashflow (at maturity) | 953.8655 | 168.3292 | 0 | 1122.1947 |  | 785.5363 | 336.6584 | Note it will take 4-5 years post development for the village to reach maturity (i.e. full churn / turnover)
|  | Investment Value (at maturity) | 5450.6597 | 961.8811 | 0 | 6412.5409 |  | 4488.7786 | 1923.7623 | Operator's Interest (including ground lease if appplicable)

## House Build Up
Design |  | 3500
Consenting |  | 10000
Laterals/ drainage |  | 15000
House | 3000 | 366000
394500
| 122 | 3233.6066
| GST | 485.041
3718.6475

## For Slides - Freehold
Formula Driven: | [6 empty] | Formula Driven:
| Freehold |  | Leasehold |  | Variance |  |  | 25% Vendor Share |  |  |  | 50% Vendor Share
| A Class | B Class | A Class | B Class | A Class | B Class |  | Hāpai | KPV | Vendor | Total | Hāpai | KPV | Vendor | Total
Shareholdings | [6 empty] | Shareholdings
A-Class | 70% | 0% | 70% | 0% | 0% | 0% | A-Class | 70% | 0% | 0% | 70% | 70% | 0% | 0% | 70%
B-Class | 0% | 30% | 0% | 30% | 0% | 0% | B-Class | 15% | 15% | 0% | 30% | 15% | 15% | 0% | 30%
Total | 70% | 30% | 70% | 30% | 0% | 0% | Total | 85% | 15% | 0% | 100% | 85% | 15% | 0% | 100%
Development Output | [6 empty] | Development Output
Peak Capital (net of preferred) | 19729.1626 | 0 | 19729.1626 | 0 | 0 | 0 | Peak Capital (net of preferred) | 19729.1626 | 0 | 0 | 19729.1626 | 19729.1626 | 0 | 0 | 19729.1626
Share of ORA Surplus | 5548.5804 | 2377.963 | 5548.5804 | 2377.963 | 0 | 0 | Share of ORA Surplus | 6737.5619 | 1188.9815 | 0 | 7926.5434 | 6737.5619 | 1188.9815 | 0 | 7926.5434
Share of Preferred Interest | 5007.8591 | 0 | 5007.8591 | 0 | 0 | 0 | Share of Preferred Interest | 5007.8591 | 0 | 0 | 5007.8591 | 5007.8591 | 0 | 0 | 5007.8591
Total | 10556.4395 | 2377.963 | 10556.4395 | 2377.963 | 0 | 0 | Total | 11745.421 | 1188.9815 | 0 | 12934.4025 | 11745.421 | 1188.9815 | 0 | 12934.4025
Margin (on share of costs) | 13.27% | n/a | 13.27% | n/a | 0% | - | Margin (on share of costs) | 14.76% | n/a | n/a | 16.26% | 14.76% | n/a | n/a | 16.26%
Margin (on share of capital) | 53.51% | n/a | 53.51% | n/a | 0% | - | Margin (on share of capital) | 59.53% | n/a | n/a | 65.56% | 59.53% | n/a | n/a | 65.56%
Long Term Investment | [6 empty] | Long Term Investment
IRR (15 year - real basis) | 14.47% | 2.98e-07% | 14.47% | 2.98e-07% | 0% | 0% | IRR (15 year - real basis) | 15.38% | n/a | n/a | 16.22% | 15.38% | n/a | n/a | 16.22%
Annual Cashflow (at maturity) | 785.5363 | 336.6584 | 785.5363 | 336.6584 | 0 | 0 | Annual Cashflow (at maturity) | 953.8655 | 168.3292 | 0 | 1122.1947 | 953.8655 | 168.3292 | 0 | 1122.1947
Investment Value (at maturity) | 4488.7786 | 1923.7623 | 4488.7786 | 1923.7623 | 0 | 0 | Investment Value (at maturity) | 5450.6597 | 961.8811 | 0 | 6412.5409 | 5450.6597 | 961.8811 | 0 | 6412.5409
Copy and Paste: | [6 empty] | Copy and Paste:
| Freehold |  | Leasehold |  | Variance |  |  | 25% Vendor Share |  |  |  | 50% Vendor Share
| A Class | B Class | A Class | B Class | A Class | B Class |  | Hāpai | KPV | Vendor | Total | Hāpai | KPV | Vendor | Total
Shareholdings | [6 empty] | Shareholdings
A-Class | 70% | 0% | 70% | 0% | 0% | 0% | A-Class | 52.5% | 0% | 17.5% | 70% | 35% | 0% | 35% | 70%
B-Class | 0% | 30% | 0% | 30% | 0% | 0% | B-Class | 15% | 15% | 0% | 30% | 15% | 15% | 0% | 30%
Total | 70% | 30% | 70% | 30% | 0% | 0% | Total | 67.5% | 15% | 17.5% | 100% | 50% | 15% | 35% | 100%
Development Output | [6 empty] | Development Output
Peak Capital (net of preferred) | 31858.3502 | 0 | 17103.8519 | 0 | 14754.4983 | 0 | Peak Capital (net of preferred) | 23893.7626 | 0 | 7964.5875 | 31858.3502 | 15929.1751 | 0 | 15929.1751 | 31858.3502
Share of ORA Surplus | 10535.8361 | 4515.3583 | 23286.532 | 9979.9423 | -12750.6959 | -5464.584 | Share of ORA Surplus | 10159.5563 | 2257.6792 | 2633.959 | 15051.1944 | 7525.5972 | 2257.6792 | 5267.9181 | 15051.1944
Share of Preferred Interest | 11251.3307 | 0 | 3794.605 | 0 | 7456.7257 | 0 | Share of Preferred Interest | 8438.498 | 0 | 2812.8327 | 11251.3307 | 5625.6654 | 0 | 5625.6654 | 11251.3307
Total | 21787.1668 | 4515.3583 | 27081.1371 | 9979.9423 | -5293.9702 | -5464.584 | Total | 18598.0543 | 2257.6792 | 5446.7917 | 26302.5252 | 13151.2626 | 2257.6792 | 10893.5834 | 26302.5252
Margin (on share of costs) | 19.72% | n/a | 27.16% | n/a | -7.437% | - | Margin (on share of costs) | 22.45% | n/a | 19.72% | 23.81% | 23.81% | n/a | 19.72% | 23.81%
Margin (on share of capital) | 68.39% | n/a | 158.3% | n/a | -89.95% | - | Margin (on share of capital) | 77.84% | n/a | 68.39% | 82.56% | 82.56% | n/a | 68.39% | 82.56%
Long Term Investment | [6 empty] | Long Term Investment
IRR (15 year - real basis) | 15.06% | 2.98e-07% | 28.84% | 2.98e-07% | -13.77% | 0% | IRR (15 year - real basis) | 16.32% | n/a | 15.06% | 16.89% | 16.89% | n/a | 15.06% | 16.89%
Annual Cashflow (at maturity) | 2062.8409 | 884.0747 | 1123.9138 | 481.6774 | 938.9271 | 402.3973 | Annual Cashflow (at maturity) | 1989.168 | 442.0373 | 515.7102 | 2946.9156 | 1473.4578 | 442.0373 | 1031.4205 | 2946.9156
Investment Value (at maturity) | 11787.6625 | 5051.8554 | 6422.3647 | 2752.442 | 5365.2978 | 2299.4133 | Investment Value (at maturity) | 11366.6745 | 2525.9277 | 2946.9156 | 16839.5178 | 8419.7589 | 2525.9277 | 5893.8312 | 16839.5178

## For Slides - Ground Lease
Formula Driven: | [6 empty] | Formula Driven:
| Freehold |  | Leasehold |  | Variance |  |  | 25% Vendor Share |  |  |  | 50% Vendor Share
| A Class | B Class | A Class | B Class | A Class | B Class |  | Hāpai | KPV | Vendor | Total | Hāpai | KPV | Vendor | Total
Shareholdings | [6 empty] | Shareholdings
A-Class | 70% | 0% | 70% | 0% | 0% | 0% | A-Class | 70% | 0% | 0% | 70% | 70% | 0% | 0% | 70%
B-Class | 0% | 30% | 0% | 30% | 0% | 0% | B-Class | 15% | 15% | 0% | 30% | 15% | 15% | 0% | 30%
Total | 70% | 30% | 70% | 30% | 0% | 0% | Total | 85% | 15% | 0% | 100% | 85% | 15% | 0% | 100%
Development Output | [6 empty] | Development Output
Peak Capital (net of preferred) | 19729.1626 | 0 | 19729.1626 | 0 | 0 | 0 | Peak Capital (net of preferred) | 19729.1626 | 0 | 0 | 19729.1626 | 19729.1626 | 0 | 0 | 19729.1626
Share of ORA Surplus | 5548.5804 | 2377.963 | 5548.5804 | 2377.963 | 0 | 0 | Share of ORA Surplus | 6737.5619 | 1188.9815 | 0 | 7926.5434 | 6737.5619 | 1188.9815 | 0 | 7926.5434
Share of Preferred Interest | 5007.8591 | 0 | 5007.8591 | 0 | 0 | 0 | Share of Preferred Interest | 5007.8591 | 0 | 0 | 5007.8591 | 5007.8591 | 0 | 0 | 5007.8591
Total | 10556.4395 | 2377.963 | 10556.4395 | 2377.963 | 0 | 0 | Total | 11745.421 | 1188.9815 | 0 | 12934.4025 | 11745.421 | 1188.9815 | 0 | 12934.4025
Margin (on share of costs) | 13.27% | n/a | 13.27% | n/a | 0% | - | Margin (on share of costs) | 14.76% | n/a | n/a | 16.26% | 14.76% | n/a | n/a | 16.26%
Margin (on share of capital) | 53.51% | n/a | 53.51% | n/a | 0% | - | Margin (on share of capital) | 59.53% | n/a | n/a | 65.56% | 59.53% | n/a | n/a | 65.56%
Long Term Investment | [6 empty] | Long Term Investment
IRR (15 year - real basis) | 14.47% | 2.98e-07% | 14.47% | 2.98e-07% | 0% | 0% | IRR (15 year - real basis) | 15.38% | n/a | n/a | 16.22% | 15.38% | n/a | n/a | 16.22%
Annual Cashflow (at maturity) | 785.5363 | 336.6584 | 785.5363 | 336.6584 | 0 | 0 | Annual Cashflow (at maturity) | 953.8655 | 168.3292 | 0 | 1122.1947 | 953.8655 | 168.3292 | 0 | 1122.1947
Investment Value (at maturity) | 4488.7786 | 1923.7623 | 4488.7786 | 1923.7623 | 0 | 0 | Investment Value (at maturity) | 5450.6597 | 961.8811 | 0 | 6412.5409 | 5450.6597 | 961.8811 | 0 | 6412.5409
Copy and Paste: | [6 empty] | Copy and Paste:
| Freehold |  | Leasehold |  | Variance |  |  | 25% Vendor Share |  |  |  | 50% Vendor Share
| A Class | B Class | A Class | B Class | A Class | B Class |  | Hāpai | KPV | Vendor | Total | Hāpai | KPV | Vendor | Total
Shareholdings | [6 empty] | Shareholdings
A-Class | 70% | 0% | 70% | 0% | 0% | 0% | A-Class | 52.5% | 0% | 17.5% | 70% | 35% | 0% | 35% | 70%
B-Class | 15% | 30% | 15% | 30% | 0% | 0% | B-Class | 15% | 15% | 0% | 30% | 15% | 15% | 0% | 30%
Total | 70% | 30% | 70% | 30% | 0% | 0% | Total | 67.5% | 15% | 17.5% | 100% | 50% | 15% | 35% | 100%
Development Output | [6 empty] | Development Output
Peak Capital (net of preferred) | 31858.3502 | 0 | 17103.8519 | 0 | 14754.4983 | 0 | Peak Capital (net of preferred) | 12827.8889 | 0 | 4275.963 | 17103.8519 | 8551.9259 | 0 | 8551.9259 | 17103.8519
Share of ORA Surplus | 10535.8361 | 4515.3583 | 23286.532 | 9979.9423 | -12750.6959 | -5464.584 | Share of ORA Surplus | 22454.8702 | 4989.9711 | 5821.633 | 33266.4743 | 16633.2372 | 4989.9711 | 11643.266 | 33266.4743
Share of Preferred Interest | 11251.3307 | 0 | 3794.605 | 0 | 7456.7257 | 0 | Share of Preferred Interest | 2845.9538 | 0 | 948.6513 | 3794.605 | 1897.3025 | 0 | 1897.3025 | 3794.605
Total | 21787.1668 | 4515.3583 | 27081.1371 | 9979.9423 | -5293.9702 | -5464.584 | Total | 25300.8239 | 4989.9711 | 6770.2843 | 37061.0793 | 18530.5397 | 4989.9711 | 13540.5685 | 37061.0793
Margin (on share of costs) | 19.72% | n/a | 27.16% | n/a | -7.437% | - | Margin (on share of costs) | 33.83% | n/a | 27.16% | 37.17% | 37.17% | n/a | 27.16% | 37.17%
Margin (on share of capital) | 68.39% | n/a | 158.3% | n/a | -89.95% | - | Margin (on share of capital) | 197.2% | n/a | 158.3% | 216.7% | 216.7% | n/a | 158.3% | 216.7%
Long Term Investment | [6 empty] | Long Term Investment
IRR (15 year - real basis) | 15.85% | 2.98e-07% | 28.74% | 2.98e-07% | -12.9% | 0% | IRR (15 year - real basis) | 32.39% | n/a | 28.84% | 34.01% | 34.01% | n/a | 28.84% | 34.01%
Annual Cashflow (at maturity) | 2062.8409 | 884.0747 | 1123.9138 | 481.6774 | 938.9271 | 402.3973 | Annual Cashflow (at maturity) | 1083.774 | 240.8387 | 280.9785 | 1605.5912 | 802.7956 | 240.8387 | 561.9569 | 1605.5912
Investment Value (at maturity) | 20628.4094 | 8840.7469 | 4979.6241 | 2134.1246 | 15648.7852 | 6706.6222 | Investment Value (at maturity) | 6192.9945 | 1376.221 | 1605.5912 | 9174.8067 | 4587.4034 | 1376.221 | 3211.1823 | 9174.8067